# Outline of Meningitis Mass Vaccination Plan

The meningitis vaccination plan should include the following information

## Introduction, Rationale and Objectives

  - Regional and district context

  - Justification, goal and specific objective(s) of meningitis mass vaccination campaign

## Profile of affected area and target population group(s)

  - Affected population profile: characteristics (e.g. size, concentration, displaced or refugee populations) and risk factors (e.g. latest vaccination, population movements, border  regions)

  - Targeted area and population including age

## Vaccine needs

  - Target vaccine coverage

  - Buffer stock and justification/rationale

  - Calculation of vaccine needs

- Coordination

  - National and local epidemic committee: composition, organization, role and involvement

  - Partners involved and roles

- Organization of the campaign

### Selection of Vaccination sites and priority areas

  - Vaccination site choice and rationale (in accordance with section 2)

  - Fixed sites vs. mobile posts

  - Expected number of vaccinations per day and per team (fixed and mobile sites)

- Social Mobilization

### Micro plan

  - Composition and Number of vaccination teams (according to estimated vaccination performance)

  - Vaccination campaign chronogram per sub-district  (including start date and duration per sub-district)

  - Supervision (including composition of the team and organization)

  - Training of vaccination  and supervisors teams

### Logistics

  - Cold chain at regional, district and vaccination post level

  - Local Transportation

  - Waste management: strategy, means, human resources

## Monitoring and evaluation

  - Use of vaccination cards or registries

  - Data collection of daily vaccination activities

    - Tools: tally sheets, synthesis sheets

    - AEFI surveillance

    - Indicators: vaccine use,  coverage/age group  and place

  - Evaluation of mass vaccination campaign

Vaccination coverage survey

selected independent company to conduct the survey

## Budget

- It is recommended to use the budget excel template available at the ICG website

- Final report of vaccination

Should include at a minimum

- Coverage

- Leftover vaccine doses (quantities and localization)

- Description of AEFIs reported

- Cost of the campaign

- Lessons learned and key implementation challenges