## Checklist Full
AAR Planning workplan: [Country], [event], Date of AAR: dd/mm/yyyy
Instructions:
1. Identify the activities to be implemented during each AAR phase
2. Identify the responsible for each activity
3. Define when each activity will be implemented (days and week)
4. Monitor the progress of your workplan with the drop-down menu in the column "Status"
Time till AAR
| Activity | Responsible | Status | 6 Weeks | 5 Weeks | 4 weeks | 3 weeks | 2 weeks | 1 week
Scoping | Select an event to review
Make available WHO AAR Guidance and Toolkit
Assign WCO focal point for AAR
Send WCO Checklist for AAR
Define the objectives of the AAR
Define the scope of the AAR
Select appropriate format for the AAR
Communicate with Regional Office and HQ AAR
Summarize required resources, timing etc in AAR concept note and share with senior management
Confirm acceptance of AAR concept note with senior CO mgt.
Share concept note with Regional Office and HQ
Build and confirm AAR team*
Participants | Participants identified
Participants invited
Participant list and directory created
Admin note & reminder sent
Per diem prepared
Facilitator Team | Build and confirm AAR team*
Identify AAR lead (national)
National facilitators identified
National facilitators invited to pre-meeting
Visa letters sent (if needed)
Airport transfers (if needed) - both ways
Accommodation booked
DSA (if appropriate)
Pre-workshop tasks | Collect the dates for the key milestones for pre-filling of the timeline
Create groups of 10 to 12 participants covering all functions / pillars identified in the concept note
Prepare trigger questions for each group
Agenda Agreed
Ministry of Health informed of presentation on emergency
Venue and Catering | Venue selected (security approved, appropriate size)
3 x quotes received if venue to be rented including lunch and coffee breaks
Catering package (meals and refreshments)
Catering confirmed and times provided
Final venue booked
Equipment and Room Layout | Supplies and equipment list sent to CO
Supplies and equipment from facilitation team prepared
Room layout and equipment agreed with venue manager
All supplies delivered and set up
Check overhead projector and 3x microphones
Ensure conference rooms are set up appropriately
Event banner (including logos)
Registration Desk set up
Printing | Name badges
Participants Manual
Registration Sheet
Agenda printed
Evaluation form printed
Post AAR | Conduct AAR debriefings (interviewees, AAR team, senior management)
Consolidate/clean notes and draft AAR report
Present initial report to Senior Management/MOH for validation
Disseminate report to agreed recipients
Share/publish AAR learning
Close adminstrative issues of AAR
Ensure AAR action plan contributes to NAPHS and are followed up
Ensure AAR final report is shared during other IHR MEF assessments including SPAR, JEE (self evaluation and mission) and simulation exercises
*See make up of an AAR Team in the Faciliators Manual for Debrief AAR

## Session by session preparation
| Equipment needed | Session preparation (to be prepared before session)
Preparation salle | Video projector | Assigning a color to each working group
| Laptop | Set up room so groups have wall space to work with
| Marker pens | Check overhead projector and 3x microphones
| Glue sticks | Set up registration desk with name badges, registration sheet etc.
Tape
Flipcharts
Session 1 | 100 colored cards (1 color per group) | Best practises and challenges matrix
| 5 packs of post its per group (1 color per group) | 2 flipchart pages for challenges and 2 for best practises per group
Groups should have space for 6 challenges and 6 best practises
Session 2 | 60 x red stickers 8mm diameter | 15 activity sheets per working group on 160 gm paper (in toolkit)
| 60 x green stickers 8mm diameter | Template file in country dropbox folder
50 x 160gm paper
Session 3 | 60 x yellow stickers 8mm diameter | the Way Forward
M and E Survey Printed

## Country Office Checklist
Country Office Activities
| Status | Responsible
Participants
Participants identified
Participants invited
Participant list and details created
Admin note & reminder sent
Per diem prepared
Preparation
Identify AAR lead (national)
National facilitators identified
National facilitators invited to pre-meeting
Composition of working groups agreed
Agenda confirmed
Ministry of Health informed of presentation on emergency on day 1
External Facilitator Team
Visa letters sent (if needed)
Airport transfers (if needed) - both ways
Accommodation booked
DSA (if appropriate)
Venue and Catering
Venue selected (security approved, appropriate size)
3 x quotes received if venue to be rented including lunch and coffee breaks
Catering package (meals and refreshments)
Catering confirmed and times provided
Final venue booked
Equipment and room layout
Supplies and equipment list sent to CO
Supplies and equipment from facilitation team prepared
Room layout and equipment agreed with venue manager
All supplies delivered and set up
Check overhead projector and 3x microphones
Ensure conference rooms are set up appropriately
Event banner (including logos)
Registration Desk set up
Printing
Name badges
Participant's manual
Facilitator's manual
Registration Sheet
Agenda Printed
Activity sheets
M and E Survey Printed
Country Office Supplies List
| Status | Responsible
A flip chart for each functional group
Flip chart paper
3 x packets marker pens
1 x scissors
5 x masking tape
1 x laptop for use with projecting presentations
1 x printer
5 x glue sticks