## Slide 1
AFTER ACTION REVIEW
Insert MoH logo
Insert event/outbreak
Country, Dates

## Slide 2
Welcome

## Slide 3: Objectives
Insert the objectives for this AAR – can include an additional more specific objectives on additional slide as needed

## Slide 4: Scope of the AAR
List the functions to be covered

## Slide 5: What is an After Action Review?
“NEVER LET A GOOD CRISIS GO TO WASTE.”
Winston Churchill

## Slide 6: The IHR Monitoring & Evaluation Framework
To measure both:
Standing capacity (Annual reporting, JEE)
Functional capacity (Simulation Exercises, After Action reviews)

## Slide 7: STATE PARTY ANNUAL REPORTING
Mandatory requirement under the IHR
Annual self- assessment completed by the country which aim to monitor progress towards full implementation of IHR
SPAR tool developed by WHO to assist SP in fulfilling this requirement
Covering 13 capacities
Tool is based on scale scoring system (quantitative)
Form is submitted to WHO and stored in a secure database
Results published on the Global Health Observatory and SPH website- Country & Regional Profiles
“States Parties and the Director-General shall report to the Health Assembly on the implementation of these Regulations as decided by the Health Assembly” - IHR Article 54
Notes: Reference document: State Party Self-Assessment Annual Reporting Tool, 2018
http://www.who.int/ihr/publications/WHO-WHE-CPI-2018.16/en/

## Slide 8: VOLUNTARY EXTERNAL EVALUATION
Voluntary, collaborative, multisectoral process which aims to evaluate IHR implementation status
Conducted upon official request from the Member State
19 technical areas using the JEE tool
Recommended to be conducted every 5 years
Two parts:
  Country Self- evaluation (3 months)
  External evaluation (5-10 days) (quantitative)
Reports publicly available
“… combine self-evaluation, peer review and voluntary external evaluations involving a combination of domestic and independent experts.” (IHR Review Committee Recommendations - Resolution WHA68.5 in May 2015)
Notes: Reference document: Joint External Evaluation, 2nd Edition, 2018
http://www.who.int/ihr/publications/WHO_HSE_GCR_2018_2/en/

## Slide 9: SIMULATION EXERCICES
Focuses on functionality
Voluntary, qualitative
Evaluation of non-real event
Help to develop, assess and test functional capabilities of emergency systems, procedures and/or mechanisms that respond to outbreaks and public health emergencies
Different types: Table top exercise, Drill, Functional exercise, Field/full-scale exercise
“… more science or evidence-based approach to assessing effective core capacities under “real-life” situations.” (IHR Review Committee Recommendations - Resolution WHA68.5 in May 2015)

## Slide 10: AFTER ACTION REVIEW
Qualitative review of actions taken to respond to an emergency as a means of identifying best practices, gaps and lessons learned
Focuses on functionality
Voluntary
Evaluation of real event, AFTER an event (within 3 months)
Involving all those involved in the event to discuss a task, event, activity or project, in an open and honest environment
Cover infectious disease, chemical and radiological-related hazards, and food safety as well as for natural and man-made disasters
“… implement in-depth reviews of significant disease outbreaks and PH events. (IHR Review Committee Recommendations - Resolution WHA68.5 in May 2015)

## Slide 11: THE 4 COMPONENTS OF THE IHR MEF IN THE PREPAREDNESS AND RESPONSE CYCLE
EVALUATING
PLANNING
ORGANIZING
TRAINING
& EQUIPING
PRACTISING
& TESTING
IMPLEMENTING
CORRECTIVE
ACTIONS
PREPAREDNESS & RESPONSE CYCLE
REVIEWING
RESPONDING
AAR
SPAR
SIMEX
Voluntary
External
Evaluation
SPAR
Voluntary
External
Evaluation
SPAR
State party annual reporting
Mandatory
Every year
SIMEX
Voluntary External Evaluation
Using the joint external evaluation tool
Voluntary
Every five years
SIMEX
Simulation exercise
Voluntary
On a regular basis
AAR
AAR
After action review
Voluntary
Following each response
Notes: It is critical to assess actions taken during a public health response in order to capitalize on best practices, identify actions for improvement, and promote individual and collective learning. The AAR provides a unique opportunity to review the functional capacity of public health and emergency response systems and to identify practical areas for continued improvement. AARs can be implemented as part of the preparedness and response cycle. (AAR Guide)

## Slide 12: WHAT IS AN AFTER ACTION REVIEW (AAR)?
AAR is a qualitative review of
actions taken
to respond to an emergency
as a means of identifying
gaps, lessons and best practices

## Slide 13: WHAT IS AN AFTER ACTION REVIEW (AAR)?
A good practice for collective learning
by bringing together
the relevant individuals
to critically and systematically
analyse actions taken to respond

## Slide 14: WHAT IS AN AFTER ACTION REVIEW (AAR)?
AAR are a constructive, collective learning opportunity,
where stakeholders of an emergency response within the health sector or between sectors,
can find common ground on how to improve preparedness and response capability

## Slide 15: AAR PRINCIPLES
Participative
Open and honest spirit
Space for experience sharing and mutual learning
Analysis of systems and processes
Oriented towards the identification of solutions
A compilation of participants perceptions

## Slide 16: WHAT AN AAR IS NOT?
AAR is not:
an external evaluation of an individual’s or a team’s performance;
an opportunity to criticise, blame or judge individuals.
AAR does not measure performance against benchmarks or key performance standards.

## Slide 17: KEY PHASES CARRIED OUT DURING AARs
OBJECTIVE OBSERVATION
Establish how actions were actually implemented during the response,
in contrast to how they are supposed to or normally happen, according to plans and procedures.
Identify the gap between planning and practice.
Analyse what worked well and what worked less well and why.
Identify actions to strengthen or improve performance
and how to follow-up.
ANALYSIS OF GAPS & BEST PRACTICES
AND CONTRIBUTING FACTORS
IDENTIFICATION OF AREAS OF IMPROVEMENT
Notes: The key phases carried out during AARs include: objective observation, analysis of gaps & best practices and contributing factors and identification of areas of improvement. To learn more about each of these key phases, click on each box.

## Slide 18: BENEFITS OF CONDUCTING AN AAR
Strengthen preparedness & response systems
Contribute to engraining critical self-evaluation around the event
Builds consensus & common vision on issues for follow-up
Allows documentation of lessons learnt
Allows individuals & cross-sectoral learning / development
Allows advocacy for support
Institutionalizes best practices
Addresses challenges
INSTITUTIONS
INDIVIDUALS
MEMBER STATES
Greater understanding of response between partners
Notes: What are the benefits of an AAR?
The outputs of an AAR are for Member States to use to strengthen the preparedness and response systems. Other benefits of conducting an AAR, include staff learning and development, greater understanding of response processes between partners and a common vision among stakeholders on how to improve. Systematic implementation of AARs can also contribute to engraining critical self-evaluation as part of the institutional culture.
The results of the AARs should be used to support other assessments undertaken as part of IHR monitoring and evaluation and can also help to build comprehensive National Action Plans for Health security (NAPHS).

## Slide 19: AAR OVERVIEW
Introduction : What should have happened and timeline of the response
Step 1 : What went well? What went less well? Why?
Step 2 : What can we do to improve for next time?
Step 3 : The Way Forward
STEP 2
STEP 3
STEP 1

## Slide 20: Rules of participation
Start and end working sessions on time
Respect different points of view
Write legibly
Be engaged
Please do not use laptops, mobile phones
Use the colored assigned to your group cards/post its throughout the workshop

## Slide 21: Facilitation Guidance
Maintain an unbiased perspective and use open-ended questions to guide the discussion.
Focus on learning. AAR is not an evaluation of performance but an opportunity to learn challenges and best practices.
Encourage people to give honest opinions.
Encourage active participation by all participants, including silent participants.
Encourage groups to write legibly on cards, post-its, and flipcharts.

## Slide 22: What to avoid during facilitation
Criticize, blame or judge the performance
Focus on the negative. An AAR is as much about recording and analyzing what worked well as about what did not work.
While the AAR is a learning framework, the teaching of participants should be avoided.
Do not allow your own opinion or experience to influence or disrupt the conversation of groups

## Slide 23: Note Taker Tips
The reporters should transcribe everything written on the cards, flip charts, sticky notes during Sessions 1, 3, 4 and 5 in the provided templates.
You will receive a template for taking notes that is in the same format as the sessions to help you record everything that is written. There is space to add additional narrative for inclusion in the report.
When additional information is discussed but not written by the group, be sure to save it for discussion during subsequent sessions.

## Slide 24: Overview of the response
Presentation of the response by the Ministry of Health
Notes: Be sure to pre load the MOH presentation

## Slide 25: AAR OVERVIEW
Introduction : What should have happened and timeline of the response
Step 1 : What went well? What went less well? Why?
Step 2 : What can we do to improve for next time?
Step 3 : The Way Forward
STEP 2
STEP 3
STEP 1

## Slide 26
Introduction : What should have happened and timeline of the response
2. Agree in plenary on the major milestones and activities and when they occurred during the outbreak. Build a common operational picture through a timeline
Agree in plenary how things should have happened during the response in the technical area under review. This may include reviewing components of:
  The strategic response plan
  An SOP
  Details discussion and agreement on the processes

## Slide 27
Introduction : What should have happened and timeline of the response
Feb
Mar
Distribution of reagents to all regions
2/2/2016
Supervision visits in high risk regions
2/11/2016
Training of Regional RRT teams
2/17/2016
Deployment RRT team to Sinidyu, Arusha, Terime, Ukerewe
2/18/2016
RRT training Mauh
3/17/2016
PHC meeting in Mwanga, Arusha...
3/18/2016
Training for water testing in regional labs
3/19/2016
DSM Data validation study
3/19/2016
Review Cholera guidelines
3/24/2016
Country-wide distribution of chlorine powder
2/3/2016
Morogoro HC recieve FCR test kits
2/3/2016
Distribution Cholera guidelines
2/4/2016
Shinyanga cholera IPC training
2/29/2016
All 9 LGAs recieve FCR test kits
3/2/2016
Morogoro water infrastructure extension
3/3/2016
Morogoro 3 cases detected food contamination
3/3/2016
Community analysis at Muanza and Singida
3/24/2016
Orientation to CHW and community leaders to intensify SocMob
3/25/2016
RC conduct targetted social mobilization Muanga, Iringa and DSM
3/25/2016

## Slide 28: AAR OVERVIEW
Introduction : What should have happened and timeline of the response
Step 1 : What went well? What went less well? Why?
Step 2 : What can we do to improve for next time?
Step 3 : The Way Forward
STEP 2
STEP 3
STEP 1

## Slide 29
Step 2 : What happened during the response?
Step 1 : What went well? What went less well? Why?
STRENGTHS
CHALLENGES
of the response
&
CONTRIBUTING
FACTORS
(root cause analysis
see next slide)
STEP 1
Notes: Notes:
- See AAR Guide – section 5.1.3 Identification of strengths, challenges and new capacities developed
- Contributing factors = enabling & limiting factors

## Slide 30
Step 2 : What happened during the response?
Step 1 : What went well? What went less well? Why?
STRENGTHS
IMPACTS
CAUSES
CAUSES
CAUSES
CHALLENGES
IMPACTS
CAUSES
CAUSES
CAUSES
LIMITING & ENABLING
FACTORS
5 WHY’s
STEP 1
Notes: AAR Guide - Box 5.2.4. Root cause analysis
Root cause analysis is a method used to identify the factors that led or contributed to success or failure in relation to a specific issue or problem identified. The root cause is a factor that leads directly to a particular outcome (good or bad). The removal of this factor will prevent the outcome from occurring. The purpose of conducting such analysis during an AAR is to identify and eventually address the root cause, if necessary, in order to prevent a negative outcome. The purpose of the analysis is to focus the interventions on those that have a long-term impact rather than relying on quick fixes.
Root cause analysis should be used when a problem is identified that clearly requires deeper examination, or for which the why of a challenges is not answered.
The “5 Whys method” is the simplest and most frequently used approach to root cause analysis. In essence, the facilitator repeatedly asks “Why?”, to progressively unpack causative factors and thus get to the root cause of a particular issue. This technique is the most appropriate in the frame of an AAR group discussion.
Use the actions described above to elaborate clear activities, responsible focal point, resources needed, and timeline for implementation.
Add a conversation between the facilitator and participant:
Participant: One of the biggest issues was that we weren’t getting the samples back from the labs fast enough
Facilitator: Why did that happen
Participant: Well we weren’t to arrange transport to and from the labs
Facilitator: Why was that, did you have no vehicles?
Participant: Yes we had vehicles available
Facilitator: so why couldn’t you use them for transporting
Participant: We could, but they had not fuel
Facilitator: Why was that?
Participant: Funds weren’t made available as the petty cash limit was too low

## Slide 31
Step 1 : What went well? What went less well? Why?
One of the biggest issues was that we couldn’t get labs results
Impossible to confirm cases
Well we weren’t able to send sample to the lab.
Why didn’t you get labs results?
1
Yes, vehicles were available
Why is that? Didn’t you have vehicles?
2
Actually, we didn’t have fuel
Why didn’t you use the vehicles?
3
We didn’t have money to buy fuel
Why was that?
4
Yes, but the petty cash limit was too low to access the funds fast enough
Why? Funds had been sent, no?
5
Conclusion: the root cause is a financial SOP, not a lab problem
5 WHY’s
STEP 1
Notes: AAR Guide - Box 5.2.4. Root cause analysis
Root cause analysis is a method used to identify the factors that led or contributed to success or failure in relation to a specific issue or problem identified. The root cause is a factor that leads directly to a particular outcome (good or bad). The removal of this factor will prevent the outcome from occurring. The purpose of conducting such analysis during an AAR is to identify and eventually address the root cause, if necessary, in order to prevent a negative outcome. The purpose of the analysis is to focus the interventions on those that have a long-term impact rather than relying on quick fixes.
Root cause analysis should be used when a problem is identified that clearly requires deeper examination, or for which the why of a challenges is not answered.
The “5 Whys method” is the simplest and most frequently used approach to root cause analysis. In essence, the facilitator repeatedly asks “Why?”, to progressively unpack causative factors and thus get to the root cause of a particular issue. This technique is the most appropriate in the frame of an AAR group discussion.
Use the actions described above to elaborate clear activities, responsible focal point, resources needed, and timeline for implementation.
Add a conversation between the facilitator and participant:
Participant: One of the biggest issues was that we weren’t getting the samples back from the labs fast enough
Facilitator: Why did that happen
Participant: Well we weren’t to arrange transport to and from the labs
Facilitator: Why was that, did you have no vehicles?
Participant: Yes we had vehicles available
Facilitator: so why couldn’t you use them for transporting
Participant: We could, but they had not fuel
Facilitator: Why was that?
Participant: Funds weren’t made available as the petty cash limit was too low

## Slide 32
Step 1 : What went well? What went less well? Why?
Using the timeline and the trigger questions, identify the challenges and best practices
For each challenge and best practice, identify the impact this has had on the response
For each challenge and best practice, identify limiting factors (for challenges) and facilitating factors (for best practices)
Identify no more than 6 key challenges and 6 key best practices
STEP 1
Notes: Encourage the groups to take some time to look at the sticky wall activities ‘what was in place?’ and ‘the timeline’ in order to identify challenges and best practices. Ie if the time line includes regular meetings with animal and human health, is this a best practice that should be identified? Similarly if there were no SoPs or guidance in your functional area identified in session one, did that make the response challenging?.

## Slide 33
Step 1 : What went well? What went less well? Why?
Best Practice / Strengths | Impact(s) | Enabling factors
Challenges | Impact(s) | Limiting Factors
Improved coordination and sharing of information for the early detection of suspected / confirmed cases and for monitoring contacts
Relationship had been established prior to the response
Willingness of all stakeholders to undertake regular meetings
Political and financial support from central level
Response not coordinated between partners, health authorities and the central level
Duplication of activities and effort
Lack of a plan for district level coordination
Partners not participating in coordination meetings
Coordination at local level ineffective
Regular cross border coordination meetings
STEP 1

## Slide 34
Step 1 : What went well? What went less well? Why?
An important definition
Best practice:
Something that was set up during the response and that improved performance or that had a positive impact
Examples:
Development of new POSs for diagnosis
Organization of cross-border meetings during the response to facilitate better coordination
STEP 1

## Slide 35
Step 1 : What went well? What went less well? Why?
Remember the objective is:
To identify the best practices and the key challenges
but also
To identify and institutionalize
new capacities
developed during the response
e.g. new SOP, new equipment purchased, new skills learned,…
NEW
STEP 1

## Slide 36: AAR OVERVIEW
Introduction : What should have happened and timeline of the response
Step 1 : What went well? What went less well? Why?
Step 2 : What can we do to improve for next time?
Step 3 : The Way Forward
STEP 2
STEP 3
STEP 1

## Slide 37
Step 2 : What can we do to improve for next time?
Institutionalize best practices
Address challenges
Development of specific activities:
to build on enabling factors
to address the limiting factors
STEP 2

## Slide 38
Step 2 : What can we do to improve for next time?
All activities need to be practical and realistic
Several activities might be necessary to address a single challenge or a best practice
Not all best practices or challenges need an activity
STEP 2

## Slide 39
Step 2 : What can we do to improve for next time?
ACTIVITY
Ensure better procurement processes in place for testing supplies
ACTIVITY
Draft and disseminate
procurement SOPs for
testing supplies.
QUIZZ: Which ones are practical activities?
OR
ACTIVITY
ACTIVITY
Implement a 3-day laboratory training for 20 staff from regional laboratories
OR
Build capacity of lab staff
STEP 2

## Slide 40
Step 2 : What can we do to improve for next time?
Referencing the challenges, best practice, impact and factors identify key activities to overcome challenges and institutionalize best practice.
Record on the activity sheets provided
Maximum 10 activities
STEP 2

## Slide 41
Step 2 : What can we do to improve for next time?
STEP 2

## Slide 42
Step 2 : What can we do to improve for next time?
Post the activities beside the good practice or challenge
STEP 2

## Slide 43
Step 2 : What can we do to improve for next time?
In your group consolidate the activities together on a flip chart.
ACTIVITIES BOARD
STEP 2

## Slide 44: AAR OVERVIEW
Introduction : What should have happened and timeline of the response
Step 1 : What went well? What went less well? Why?
Step 2 : What can we do to improve for next time?
Step 3 : The Way Forward
STEP 2
STEP 3
STEP 1

## Slide 45
Step 3 : The Way Forward
In plenary discuss and agree on:
What can be done to ensure the implementation of the activities identified during this workshop?
STEP 3

## Slide 46
Thanks for your attention and active contribution during the AAR!