## Checklist Full
Planning Checklist Key Informant Interview AAR: [Country], [Event], Date of AAR: dd/mm/yyyy
1. Identify the activities to be implemented during each AAR phase
2. Identify the responsible for each activity
3. Define when each activity will be implemented (days and week)
4. Monitor the progress of your workplan with the drop-down menu in the column "Status"
Duration of AAR
| Activity | Responsible | Status | 6 Weeks | 5 Weeks | 4 weeks | 3 weeks | 2 weeks | 1 week
Scoping | Select an event to review
Make available WHO AAR Guide and Toolkit
Assign WCO focal point for AAR
Send WCO Checklist for WCO for AAR
Define the overall objectives of the AAR
Define the scope of the AAR
Communicate with Regional Office and HQ AAR
Summarize required resources, timing etc in AAR concept note and share with senior management
Confirm acceptance of AAR concept note with senior CO mgt.
Share concept note with Regional Office and HQ
Timeline of AAR agreed
Build and confirm AAR team*
Participants | Identify those involved in AAR
Send introductory email to all those to be interviewed
Schedule interviews remotely (videoconference, skype, webex, …) and when in country
Focus groups identified (where applicable) and planned
Send out email for feedback with excel feedback form survey
AAR Team | Build and confirm AAR team
Identify AAR lead (see ToR in toolkit)
Identify AAR team members
Identify incountry support needs
Background Docs | Prepare and share background documents with AAR team
Read in on background documents
Mission to country/region | Arrange travel for mission to country/region, if necessary
Security clearance
Visa letters sent (if needed)
Airport transfers (if needed) - both ways
Accommodation booked
Per diem (if appropriate)
Report Drafting | Collate interview data and begin drafting, follow up as needed
Prepare and circulate draft for circulation for comment
Comments received and collated
AAR Finalisation | Conduct AAR debriefing and finalisation (interviewees, AAR team, senior management)
Consolidate/clean notes and draft AAR report
Present initial report to Senior Management/MOH for validation
Disseminate report to agreed recipients
Share/publish AAR learning
Close adminstrative issues of AAR
Ensure AAR action plan contributes to NAPHS and are followed up
Ensure AAR final report is shared during other IHR MEF assessments including SPAR, JEE (self evaluation and mission) and simulation exercises
*See ToR of team lead for KII AAR in Toolkit that describes make up of team