## Scope of AAR
SCOPE of the ARR
Response phase | Function | Expected Output | AAR-specific expected outcome | Core Capacity in State Party Annual Reporting
| Which particular function of the response is assessed? | In relation to the event selected for the After action review, this column describes the expected outcomes for the review for each function. |  | What Core Capacity is assessed?
Prepare | Emergency Preparedness and Response Planning | To review the relevance emergency preparedness and response plans to the event under review. Did the plans contribute to a timely and effective implementation of the response including many of the below functions e.g. coordination, information managenet, finance, etc? |  | Core Capacity 12: Preparedness
| Risk profiling | To review the relevance of risk profiling activities to the event in review. Review how THE prioirization of risks allowed for preparedness measures to undertaken and enable an effective and timely response.
| National Legislation | To review, in the context of the response of an emergency, the legal public health framework, including policies and legislislation, governing and providing authorities for detection, assessment, notification, response and recovery. |  | Core Capacity 1: national legislation, policy and financing
Detect | Surveillance and early warning | To review functioning of the surveillance and early warning system to timely collect, analyse and interpret signals; to diffuse information to decision-makers and to trigger appropriate response action. |  | Core Capacity 9: Real time surveillance
| National Laboratory system | To review the functioning of the National Laboratory System to provide a timely confirmation of the pathogen, including the collection and safe transport of specimens to national and international reference laboratories, as necessary. |  | Core Capacity 8: National Laboratory System
Assess and Inform | Rapid response team operations | To review the operations of the Rapid Response Team including its activation, composition deployment and equipping. In addition, to review the outcomes of the rapid response team investigation during the event to enable decision-making and implement initial response actions. |  | Core Capacity 9: Real time surveillance
| Risk assessment and response activation | To review actions takent to assess the risk of the emergency, to assign "grade" to the event and initiate timely and commensurate response actions |  | Core Capacity 13: Emergency Response Operations
| IHR Notification | To review the actions taken to notify WHO, OIE or other international authorities in line with obligations for notification. |  | Core Capacity 10- Reporting
Respond | Emergency Response operations | To review the operational, tactical and strategic coordination of the response, including the operations of a incident management system (IMS) and emergency operations centre (EOC) for decision making, management and quick intervention |  | Core Capacity 13: Emergency Response Operations
| Case management and fatality management | To review actions taken to treat cases and to manage fatalities resulting from the emergency |  | Core Capacity 13: Emergency Response Operations
IPC and WASH
Vaccination
| Intersectoral and stakeholder coordination | To review the functioning of procedures and plaftforms for multisectoral coordination for enabling information dissemination, resource mobiliziation and sharing, efficient decision making and effective distribution of roles and responsibilities. This includes collaboration with other sectors of governmant and national and international partners, including UN, NGOs and private industry. |  | Core Capacity 14: Linking Public Health and Security Authorities and/or other relevant sector
| Logistics (Supply) | To review the availability, distribution and dissemination of stockpiled goods for a timely and effective response. In addition, to review the procedures for national and international procurement including customs arrangements, and service contracting. |  | Core Capacity 15: Medical Countermeasures and Personnel Deployment
| Surge Capacity | To review the capacity to timely increase human, material and financial resources and to safely deploy HR, efficiency for scaling up national and/or international HR (admin) |  | Core Capacity 15: Medical Countermeasures and Personnel Deployment
| Risk communication and community mobilization | To review the functioning of risk communciation and community engagement plans in terms of available resources, staff and coordination during the response. |  | Core Capacity 16: Risk Communication
| Public Communication | To review the effectiveness of existing plans for public communication in term of definition of public statements, designation of spoke person and use of media/language and to assess their effectiveness in building transparency and trust and in managing public concerns. |  | Core Capacity 16: Risk Communication
| Information Management | To review action taken to manage and diseminate information in different forms and to diferent audience for the purpose of allowing decision making, raising awareness or mobilizing resources and support from national or international donors.
| Integrated vector management | To review actions taken to limit or eliminate the presence of vectors in order to interupt transmission of disease
| Finance Management | To review actions taken to management funds during the response including the availability, accessing funds, timeliness and safety of payment and cash managmement and the maintenance of a financial overview and accountancy during the emergency.
Phase out and Post Emergency | Response phase-out and closing | To review actions taken to declare the end of the emergency and to phase-out response activities in timely and effective manner.
| Recovery | To review effectiveness in engaging in health sector recovery following the emergency, including coordination with other sectors in managing comprehensive recovery programme
| Health system strengthening | To review actions taken to or needed to strengthen and establish resilient health system in order to maintain routine health services during an emergency.
Specific Capacities for IHR events
IHR specifc hazard | Point of Entry | Under development
| Chemical event | Under development
| Radiology related event | Under development
| Food safety Event | Under development
Note on C8: David Cuenca: here, it is going more than detection and alert verification. Can make sense to create a single point for all legislation etc in place but in that case, better to kkep it in preparedness as it was in a previous version.
Note on B12: David Cuenca: should we merge risk assessment and RRT? Also, if risk assessment enable grading, this is an output of the rrt deployment, that's why it was initially out in response, as first step of the response. After agreement, this is also how it has been placed in the ERP. I also propose to change the name by "grading and response activation" as assessment is more under RRT.
Note on C32: David Cuenca: I removed the mention to HR mobility because it is in the following function

## Emergency preparedness planning
Emergency Preparedness and Response Planning
Description: To review the relevance of emergency preparedness and response planning to the event under review. Did the plans contribute to a timely and effective implementation of the response including many of the functions of the response
Trigger questions
| Questions | Discussion points
Document | Does an Emergency preparedness and response plan exist? | Existence of a EPRP and/or National multi-risk plan, with role of health w/in National multi-risk plan
Identify and analyse | Was the plan used during the emergency? Did the time and resources invested in preparedness measures allow for effective and timely action? | Use and usefulness of ERP during the emergency, staff level of preparation/training, functionality of coordination platforms as described in ERP, functionality of ressources mobilization and deployment
Improve | Which element of preparedness were the main enablers of the response? | relevance of its contents/structure, clarification of roles and responsibilities
| Did the response highlight specific weaknesses in the preparedness process? | relevance of its contents/structure, clarification of roles and responsibilities
Relevant documents to review
National emergency response plan
Contigency plan
National IHR implementation plan
Logistics stockpiling plans
Exercise programmes and exercise reports
List of trainings and trainings curriculum
Indicators
Additional questions

## Risk profiling
Risk profiling
Description: To review the relevance of risk profiling activities to the event in review. Review how the prioirization of risks allowed for preparedness measures to be undertaken and enable an effective and timely response.
Trigger questions
| Questions | Discussion points
Document | Did the national risk profile of the country include the hazard under review? | Relevance/adequacy of the risk profiling
| What was the risk level assigned to this hazard? In hindsight, does this seem correct? | Usefulness in identifying and classifying the actual emergency
Identify and analyse | Did the risk profiling activities, contribute to an overall enhanced state of readiness for this hazard? | Implementation of preparedness measures recommended by risk profiling
| Did the risk profiling activities contribute to sensitize and engage relevant stakeholders/actors in the response? | Implication of relevant actors in the risk profiling activity and how it enabled their implication in the response
Improve | How could risk profiling activities have better anticipated the impact of this hazard or the health system? | Identification of Best practise and weaknesses in the risk profiling
Relevant documents to review
National emergency preparedness and response plan
Risk profiling results STAR
Vulnerabiligy mapping Report (VRAM)
Logistics stockpiling plans
Indicators
Additional questions

## National Legislation
National Legislation
Description: To review, in the context of the response of an emergency, the legal public health framework, including policies and legislislation, governing and providing authorities for detection, assessment, notification, response and recovery.
Trigger questions
| Questions | Discussion points
Document | What national legislation and policies exist for enabling different elements of the management of the event? | Existence and relevance of the legislative framework
Identify and analyse | Did national legislation enable an effective detection, assessment and response? | Clarification of coordination and management organs, roles and responsibilities for surveillance, detection and response, availability of funds and mechanism for ressources mobilization
Improve | Did the response highlight any weaknesses or strength in existing legislation or policies? | Summary of adequacy and relavance of the legislative framework
Relevant documents to review
National emergency response plan
National legislations relevant emergency surveillance, detection and response
Indicators
Additional questions

## Surveillance and early warning
Surveillance and early warning
Description: To review the functioning of the surveillance and early warning system to timely collect, analyse and interpret signals; to diffuse information to decision-makers and to trigger appropriate response action.
Trigger questions
| Questions | Discussion points
Document | How should surveillance and/or early warning systems detect an event of this kind? | Surveillance system and triggers in place, coordination and information sharing systems in place
| How is analysis and transmission of information for decision making supposed to take place? | Existence of SOPs and coordination/information sharing protocols
Identify and analyse | How did surveillance and/or alert systems detect the event? | Existence of case definition in health centres, ability of mechanism for rumour/alert validation at central level, timeliness of first laboratory data, effectiveness of community base surveillance mechanisms
| Were their sufficient resources to undertake surveillance and early warning? | Human, financial, material, connectivity issues related to surveillance
| How was epidemiological data analysed and used to enable a response? | Effectiveness of channel of communication from local to national level and viceversa, information sharing with partners and sectors
| How did partners or other sectors contribute to surveillance and early warning? How was information shared? | Implication and role of the other sectors, partners and the private sector. Timeliness and
| How were surveillance activities adapted or reinforced through the course of the response? | Training of staff, equipment, coordination, SOPs etc: effectiveness of the system to detect the actual emergency
| How did the surveillance system detect the end of the outbreak/end of the emergency situation? | Effectiveness of monitoring mechanisms and efficiency in decision making and information sharing within the MoH
Improve | What actions taken enabled an efficient and timely detection of the event? | Best practise in surveillance system
| What challenges were encountered in detecting the event? | Weaknesses in surveillance system
Relevant documents to review
National emergency response plan
Surveillance plans
IDSR plans
Surveillance case definitions
Indicators
Timeliness |  | % of sites reporting on a timely basis during outbreak
Reporting completeness |  | % of sites reporting during outbreak
Completeness of data reported |  | % of contacts followed up over the course of contract tracing
Contact tracing
Additional questions

## National laboratory systems
National Laboratory system
Description: To review the functioning of the National Laboratory System to provide timely confirmation of the pathogen, including the collection and safe transport of specimens to national and international reference laboratories, as necessary.
Trigger questions
| Questions | Discussion points
Document | How does the national laboratory system function? | Existence of algorithms SOPs etc, coordination human/animal labs,
| What is the process for transporting specimen to national and/or international reference laboratory? | Existence of SOPs, certified staff, systems/agreements/resources in place for national and international transport
| What are the procedures for information sharing and decision making between laboratories and epidemiological services? With animal health laboratories? | Coordination lab/surveillance system, coordination human/animal labs, coordination with private sector and/or other relevant actors, information sharing and decision making mechanisms in place
Identify and analyse | What was the process for laboratory confirmation? How was information coming from the laboratories managed? | Timely confirmation of first case, sample collection, transport, reception, reporting of information to surveillance to treating physician. Laboratory capacity maintained throughout the outbreak.
| Were plans and SOPs for laboratory testing adequate to respond to the event? | Usefulness of plans and SOPS existence of quality monitoring and corrective measures
| Were there sufficient resources (human, material and financial) available to provide consistent laboratory support during the outbreak? | Availability of reagents and material, Functioning laboratory hardware, trained staff, scaling up capacity,
| How did coordination and information sharing with other laboratories in the health sector and in other sectors function? | Coordination and information sharing with other laboratories with in health (regional, local), with other sectors (animal, environmental) and private laboratories. Sharing protocols, quality control and results.
| How was the international reference laboratory involved in confirming the event? | Availability of equipment/means for packaging and transport, availability of certified staff, coordination/communication with reference laboratory
| Did any accident or other any biosafety incident occur? If yes, what were the cause? | IPC in place, effectiveness of laboratory security and safety SOPs, qualified staff
Improve | What actions taken allowed for timely and efficient laboratory confirmation/verificiataion of the event? | Strength of laboratory system
| what challenges were encountered in confirming and verifying the laboratory diagnosis? | Weaknesses of laboratory system
Relevant documents to review
National emergency preparedness and response plan
IDSR Manual
Laboratory protocols
Indicators
Time (or average time) between detection and sample taken
Time (or average time) between sample collection and confirmation
Quality of samples (proportion
False positives / false negatives
Additional questions
How was the surge of laboratory capacity managed over the course of the oubreak?
Were laboratory preparedness measured effective in allowing timely confirmation? |  | Effectiveness of prepositioning, training,

## Rapid Response Team
Rapid Response Team (RRT) oeprations
Description: To review the operations of the Rapid Response Team including its activation, composition deployment and equipping. In addition, to review the outcomes of the rapid response team investigation during the event to enable decision-making and implement initial response actions.
Trigger questions
| Questions | Discussion points
Document | What is the rapid response team (RRT) legal framework and how is its role defined? | Existence of RRT legal framework, Formal constitution and nomination of RRT members, RRT line management defined,
| What is the activation process for the RRT? | Existence of RRT activation protocol, access to ressources for deployment pre-identified
Identify and analyse | How was the RRT activated and constituted in response to this event? | Adequacy of team composition, effectiveness of RRT activation protocol,clarity in roles and responsibilities within RRT,
| What activities did the RRT carryout during this event? How was the role of the RRT coordinated with local/regional/national teams? | Roles and responsibilities of the RRT, operations undertaken, coordination with local/regional authorities and partners, effectiveness of communication lines and RRT coordination/management, effectiveness of decision taking processes
| Did plans and procedures of the RRT provide guidance on the roles, responsibilities? | effectiveness of RRT management and coordination, clarity in RRT members roles and responsabilities
| What was the role/implication of other actors or partners in the operations of the RRT? | Intersectorial coordination, involvment of other sectors, Ministries, partners etc.
| Was the RRT adequately equipped for undertaking activities? | Trained staff, availability of equipment and tools, transport, timely availability of resources for RRT deployment
| How were the findings of the RRT used for decision making | Quality/usefulness of first findings/reports,
Improve | What actions taken during the event allowed for a better than expected performance of the RRT? | RRT best practises
| What challenges were encountered in the operations of the RRT or in investigating rumors? | Weaknesses of RRT
Relevant documents to review
National emergency preparedness and response plan
RRT Terms of Reference
RRT SOPs
RRT investigation reports
RRT Situational reports
Indicators
Time to activate and deploy to the field
RRT team composition during the outbreak
Additional questions

## Risk assessment and activation
Risk assessment and response activation
Description: To review actions takent to assess the risk of the emergency, to assign "grade" to the event and initiate timely and commensurate response actions
Trigger questions
| Questions | Discussion points
Document | What is the process for assessing the risk of an event? | Existence of protocols determining actions to be taken, information channel to be followed and information to be provided in order to inform decision making for grading an emergency
| How should the risk assessment trigger the activation of a response or plan (such as EOC, ERP, CONOPS, SOPs, coordination platforms, etc)? | Existence of triggers and pre-defined models of coordination/management of a response depending on the level of emergency activation
| How should the emergency declaration and grading be done? | Existence of decision making channel, clarity in responsabilities for emergency grading and declaration, clarity for information and communication channels to public and stakeholders (including notification)
Identify and analyse | How did the risk assessment process happen during the event? | Effectiveness of risk assessment process and activation protocols, resources timely available, clarity in roles and responsabilities for risk assessment, clarity on risk assessment mandate and expected outputs
| Were the appropriate stakeholders involved in the risk assessment? | Effectiveness of sectoral and multisectoral coordination and complementarities, clarity in roles and responsabilitites within stakeholders, effectiveness in expertise and ressources sharing among stakeholders
| Was sufficient information available to adequately assess the risk? | Qualitiy of data available, training and competencies of health strutures staff, collaboration/complementarities in between risk assessment team and health structure staff
| How did the risk assessment contribute to activating response structures (Incident Management System/EOC) or a response plan and declaration of the emergency? | Timeliness, information sharing channels and quality of information provided by risk assessment for response activation and oficial emergency declaration, adequacy of emergency response coordination/management model implemented (IMS)
| How has emergency grading and declaration been done and communicated to public and stakeholders (including notification if relevant)? | Effectiveness of decision making channels and communication channels
Improve | What actions taken during the event enabled the for grading, risk assessment or activation? | Best practises in grading and activation protocol
| What challenges were encountered during the grading, risk assessment or activation proccess? | Weaknesses in grading and activation protocol
Relevant documents to review
National emergency preparedness and response plan
Risk assessment report
Statement declaring emergency
Minutes of risk assessment meeting
Senior management briefing
Indicators
Historical data on risk assessment of similar event
Time to activitate EOC / response plan
Additional questions
If formal risk assessment did not occur and no protocol exists, how was the response activated? Did this enable a timely and effective response?

## Notification
IHR notification
Description: To review the actions taken to notify WHO, OIE or other international authorities in line with obligations for notification.
Trigger questions
| Questions | Discussion points
Document | What are the procedures in place for notifying WHO? And other international partners, if applicable? | Existence of legislation/SOPs for reporting PHEIC
| What are the procedures in place for notifying OIE? | Existence of legislation/SOPs for reporting PHEIC
Identify and analyse | How did the notification procedure to WHO and other international partners occur during this event? | Existence of trained and operational NFP, effectiveness of legislation/SOPs for reporting PHEIC to WHO and other partners, use of formal mechanism for notification
Improve | What actions were taken during the notification process that resulted in a better than expected performance? | Best practises for notification
| What challenges were encountered during the notification process ? | Weaknesses for notification
Relevant documents to review
National emergency preparedness and response plan
International Health Regulations (IHR)
Indicators
Time between detection, assessment and notification to WHO
Additional questions
If formal risk assessment did not occur and no protocol exists, how was the response activated? Did this enable a timely and effective response?

## Intersectoral coordination
Intersectoral and stakeholder coordination
Description: To review the functioning of procedures and plaftforms for multisectoral coordination for enabling information dissemination, resource mobiliziation and sharing, efficient decision making and effective distribution of roles and responsibilities. This includes collaboration with other sectors of governmant and national and international partners, including UN, NGOs, donors and private industry.
Trigger questions
| Questions | Discussion points
Document | What are the existing mechanisms for multisectoral coordination ? How should they be activated? | Existence of multisectorial ERP or contingency plans and existence of activation procedures
| What are existing mechanisms for coordinating international and national partners (UN, NGOs, NGO, etc)? | Existence of coordination mechanisms
Identify and analyse | How did multisectoral coordination take place during the emergency? | Efficiency of information sharing and decision making processes, efficiency in stakeholders mobilization, clarity in roles and responsibilities, accountability mechanisms, enhanced role and responsibilities for health sector
| How did the coordination of international and national partners (UN, NGOs, IGO, etc) take place? | Coordination mechanisms applied, transition process between steady situation and emergency situation, clarity in roles and responsibilities of actors
| Was a joint Inter-Agency/multisectoral response plan developed? How did this contribute to enhance the response? | Use and usefulness of multisectoral ERP, contingency plans etc
| Were sufficient resources (human, material and financial) available for multisectoral coordination? | trained staff for coordination across sectors or with health partners, material or technology needs met, financial resources
| Was the health cluster activated and operational? Was it effective for coordinating roles and responsibilities and for ensuring complementarity between partners? | Efficiency of information sharing and decision making processes, efficiency in stakeholders mobilization, clarity in roles and responsibilities, accountability mechanisms, WHO role in coordinating health partners.
Improve | What actions enabled coordination with other sectors or partners? | Strength in multisectorial and I-A coordination
| What challenges were encountered in coordination with other sectors or with international and national partners (UN, NGOs, IGO, etc)? | Weaknesses in multisectorial and I-A coordination
Relevant documents to review
National emergency preparedness and response plan
Multisectoral responses plans
Memoranda of understanding between sectors/partners in response
Situational reports and distribution lists
Meeting summaries or minutes
4 Ws mapping
Indicators
Frequency of coordination meetings
Number of partners participating
Interval between start of emergency and activitation of intersectoral coordination
Additional questions
Did the private sector participate in coordination platforms? What was their role and how was the relation between private and public sector has been managed
How was coordination with national and international donors managed?

## Operational Coordination
Emergency response operations
Description: To review the operational, tactical and strategic coordination of the response, including the operations of a incident management system (IMS) and emergency operations centre (EOC) for decision making, management and quick intervention
Trigger questions
| Questions | Discussion points
Document | What is the operational coordination mechanism within the Ministry of health? | Existence of EOC or other kind of organizational structure for emergency response coordination
| How is coordination with different levels of the Minstrty supposed to happen including at the field level? | Existence of coordination models for internal health system coordination
Identify and analyse | How was the coordination of response actions at different administrative levels (local, regional and national) undertaken during the event? | Effectiveness of operational coordination/management, decision making and operational communication between strategic (senior management), operational (EOC/IMS) and tactical (field) levels
| Were sufficient resources (human, financial and material) sufficient to adequately coordinate the response operations at each level? | Trained staff for coordination/incident management, communication or other materials needs,
| Were existing contigency/response plans for this emergency effective in identifying actions, making decisions and communicating information? | Complementarity and coordination within health system/health division and partners, usefulness of contingency plan for relevant strategy design and efficient operation implementation, incorporation/benefits of previous lessons learned
| How effective were the operations of the public health emergency operations centre? | Timely availability of funds, availability and effectiveness of EOC SOPs and EOC activation protocol, identified and trained staff, knowledge of individual roles, responsibilities and functions, EOC coordination mechanism in place, infrastructure and technology available and functional
Improve | What actions taken enabled operational coordination between levels of the ministry of health or between strategic, operations and tactical levels? | Best practises in emergency response coordination
| What challenges were encountered operational coordination ? | Weaknesses in emergency response coordination
Relevant documents to review
National emergency and response plan
Standard operating procedures
EOC Concept of Operations
Situational reports
Indicators
Date of activation of the Health EOC/beginning of coordination meetings
Frequency of coordination meetings
Frequency of situational reports?
Date of declaration of emergency/ end of emergency?
Additional questions

## Case management
Case management and fatality management
Description: To review actions taken to treat cases and to manage fatalities resulting from the emergency
Trigger questions
| Questions | Discussion points
Document | What are the existing procedures for case management and fatality management for this type of emergency? | Existence of case definition, SOPs etc
| What is the process for patient referral or transport? | Existence of SOPs and identified means of transport
| What are the existing procedures for infection prevention and control of health care workers? For community? | Existence of SOPs and defined prevention measures for community
Identify and analyse | How were cases and fatalities managed during the emergency? | Availability and relevance of SOPs, existence of trained and equipped staff, quality of patient management
| How were patients transported / referred between healthcare facilitaties? | Referral and counter-referral system, means of transport
| Were infection prevention and control measures implemented during the emergency effective in preventing infection in a HC setting or in the community? | Efficiency of IPC SOPs, availability of trained and equipped staff, absence of infection/incident affecting staff, effectiveness of prevention measures at community level
| How was the coordination of case/fatality management undertaken between sectors and partners? | Coordination between sectors/partners on case management, sharing clinical protocols, patient referral, information sharing, resources
| Was the necessary equipment/material/resources for case management and personal protection available? | Availability of adequate resources for case management and staff protection (in quantity and quality), mechanisms and procedures in place for timely access to required resources and equipment
| What was the role of the public sector and/or other actors in case management | Role and interactions with private sector and/or other relevant actors (ex: NGO)
| How was the case management financed? Was it for free for patients? | Access to free treatment
Improve | What best practises can be identified for preventing infection in HCWs or in the community? | Best practises in IPC and preventive measures
| What best practises can be identified the management of cases/fatalities? | Best practises in case and fatality management
| What challenges were encountered in the management of cases/fatalities? | Weaknesses in case and fatality management
| What challenges were encountered in implementing IPC measures in healthcare setting or in the community? | Weaknesses in IPC and preventive measures
Relevant documents to review
National emergency preparedness and response plan
Clinical management SOPs
Indicators
Case fatality rate (CFR)
Total case numbers and hospitalization rate
Additional questions
How was hazardous waste managed during the event?

## IPC and WASH
Infection prevention and control and WASH
Description: to review infection prevention and control measures and WASH activities implemented in healthcare and community settings
Trigger questions
| Questions | Discussion points
Document | What are the existing plans and preparedness measures implemented for ensuring water supply in health structures and in communities? | Existance of plans, SOP, stockpiles
| What are the existing plans, SOPs and preparedness measures for protecting health staff and communities from contaminations? | Existance of plans, SOP, stockpiles
| What are the existing plans and SOPs for waste management within health structures? | Existance of plans, SOP
Were IPC plans and procedures sufficient to for the implementation of measures during the emergency?
| Were sufficient resources available to protect staff from infection (PPE), waste deposable and decontamination? | Efficiency of IPC SOPs, availability of trained and equipped staff, absence of infection/incident affecting staff, effectiveness of prevention measures at community level
| How was waste managed in health structures? | Efficiency of waste management SOPs, availability of trained and equipped staff
Were sufficient resources for WASH activities available?
| How was the water supply ensured in the health facilities? In communities? | Relevance and efficiency of water supply activities, quantity and quality of water in accordance with SPHERE standards, availability of qualified staff
| Were sufficient resouces for implementing IPC measures and waste management in healthcare facilities available? | Availability of adequate ressources for water supply, waste management and staff protection (in quantity and quality), mechanisms and procedures in place for timely access to required ressources and equipment
| How was coordination with other sectors, including private sector, ensured in the implementation of IPC measures in HC and communities, and for WASH activities? | Role and interactions with private sector and/or other relevant actors (ex: NGO), efficiency of coordination mechanisms in place, complementarity in actions
Improve | What best practices can be identified for ensuring water supply in health facilitities and communities? | Strength in water supply
| What bes practices can be identified for preventing infections and waste managment? | Strength in IPC and waste management
| What were the challenges for water supply in health facilities and communitites? | Weaknesses in water supply
| What were the challenges in IPC and waste management? | Weaknesses in IPC and waste management
Relevant documents to review
Available SOPs (handwashing, donning and doffing, decontamination, etc)
Infection prevention and control strategy
Indicators
Number of healthcare workers infected
Availability of PPE, decontamination equipment
Additional questions

## Vaccination
Vaccination
Description: To review actions taken to limit or eliminate the presence of vectors in order to interupt transmission of disease
Trigger questions
| Questions | Discussion points
Document | What are the existing supports and frameworks for defining a vaccination campaign strategy? | Existence and knowledge of policies, plans, strategies for vaccination campaign
| What are the structures and ressources avalaible for conducting a vaccination campaign? | preparedness measures, availability of services, trained staff, equipment and stocks for vaccination
Identify and analyse | How was the vaccination strategy, target group and geographical areas developed? | Use and usefullness of existing vaccination campaign strategies, plans, geographical areas, Relevance and efficiency of the vaccination coverage
How was the overall implementation of the vaccination strategy managed?
| How was the implementation of the vaccination coordinated within the health sector? | Complementarity and coordination mechanism of partners
| How were the target groups for informed or communicated with during the vaccination campaign | Relevance and efficiency of information and communication activities
How was coordination with partners and other sectors managed during the vaccination.?
| Were sufficient resources were available for the vaccination and how were mobilized? | Timely availavility of trained and qualified human ressources, transport, financial, etc
| How vaccines have been supplied, stored and transported? | Availability of stocks, cold chain, means of transport. Existence of vaccine purchase policies, timeliness of vaccine availability, existence of cold chain management capacities, effectiveness in storing and distributing vaccines
| How was waste management associated with the vaccination managed? | Availability of waste management policies, equipment, trained staff and ressources
Improve | What actions enabled a timely and effective vaccination campaign? | Strength in vaccination campaign
| What actions enabled a timely and effective vaccination campaign? | Weaknesses in vaccination campaign
Relevant documents to review
National vaccination strategy or operational plan
Response plan
Vaccine micro-plans
Cold chain mapping
Indicators
% Vaccine coveragein campaign
Time interval between arrival/purchase of vaccine and start of vaccination campaign
Additional questions

## Vector control
integrated vector Management
Description: To review actions taken to limit or eliminate the presence of vectors in order to interupt transmission of disease
Trigger questions
| Questions | Discussion points
Document | What are the policies, plans and SOP existing for vector control? | Existance and knwoledge of national plans, SOP etc
| What ressources and capacities for vector control exist in the country? | Existance of ressource mobilization mechanisms and equipment
Identify and analyse | What vector control measures were implemented during the emergency and how did this impact the evolution of the outbreak? | Relevance of key activities implemented, existance of qualified staff and equipments
How effectively was the integrated vector management plan implemented?
| How were communities communicated with during vector control activities? Did communities accepted and support vector control strategy? | Existance and efficiency of social mobilization and risk communication plan and activities
| How was intersectorial coordination/collaboration managed? How this contribute to the efficiency of vector control measures? | Existance and relevance of intersectorial coordination, involvment of partners and other ministeries and competent authorities, clarity in roles and responsabilities, efficiency in ressources sharing
| Were sufficient resources available and accessible for vector control activities? | Efficiency in financial ressource mobilization and management, Existance of stockpiles, efficiency in stockpile mobilization and managment,
| Were resistance pattern to the chemical products used for vector control detected? How has resistance monitored and managed? | Adecuacy of chemical products used, monitoring of potencial resistances, capacity of adaptation
| How were chemicals and equipment supplied, stored and distributed during vectorl control activities? | Efficiency of supply, storage and distribution mechanisms
Improve | What measures/capacities enabled efficiency in vector control? | Best practices in vector control
| What challenges were faced in vector control? | Challenges in vector control
Relevant documents to review
Vector control guidelines
Existing training materials
Indicators
Additional questions
| What are the vector control measures taken at health facilities level? | Relevance of key activities implemented for staff and patients protection within health structures, availability of qualified staff and equipments

## Logistics
Logistics (Supply)
Description: To review the availability, distribution and dissemination of stockpiled goods for a timely and effective response. In addition, to review the procedures for national and international procurement including customs arrangements, and service contracting.
Trigger questions
| Questions | Discussion points
Document | How does the supply chain function during the management of an emergency? | Existence of supply policies (national and intl purchases), stock management procedures and systems for asset distribution
| What plans/procedures exist for preposition of essential material for the management of an emergency? | Existance of stockpiles at national and/or regional level, existance of procedures to access and deploy stockpiles, identified transport ressources and/or transport strategy for dispatch of goods
| What are the procedures in place for managing the vehicle fleet? | Existence of a fleet management system
Identify and analyse | How was supply chain managed during this emergency? | Availability of stockpiles, efficiency of purchase policies and procedures, timeliness and efficiency of distribution system, efficiency of control measures in place
| Was the prepositioning of essential material effective in enabling a timely and efficient response? | Prepositioning of material, efficiency of procedures for deploying stockpiles, efficiency of means of transport for deployment of goods
| Were sufficient resources (human, equipment and financial) available to provide logistics support during the event? | human resources capacity, necessary tools and material to undertake logistic management, agility to access material and financial ressources for logistics activities
| How was fleet management undertaken during the response? | Management of vehicles and transport of medical and non-medical assets allows for timely implementation of response actions, fleet management system in place, vehicules for transport of goods timely available (own by MoH, rent, partners etc), existance of identified potential vehicules location (private sector) etc
| Were there other partners or sectors involved in delivering logistics services? What were their role(s) and how was it coordinated and managed? | Involvement and coordination of partners and sectors (including private sector if relevant)
Improve | What actions taken enabled the supply of medical and non-medical assets? | Best practise in supply, stock management and assets distribution
| What challenges were encountered in the supply of medical or non-medical assets? | Weaknesses in supply, stock management and assets distribution
| What challenges were encountered in fleet management? | Weaknesses in fleet management
Relevant documents to review
National emergency preparedness and response plan
list of stockpiled material
National warehouse inventory
Indicators
Average duration of internal shipment of material
Average duration of international shipment of material
Average time of material in customs
Additional questions

## Surge capacity
Surge Capacity
Description: To review the capacity to timely increase human, material and financial resources and to safely deploy HR, efficiency for scaling up national and/or international HR (admin)
Trigger questions
| Questions | Discussion points
Document | What mechanisms are in place for scaling up operations? | Existing scale up mechanisms
| Is there an emergency roster and procedure for the recruitment and transport for a surge HR capacity? | Existing mechanisms for HR scale up and HR management
Identify and analyse | What was the process for scaling-up HR, material and funding needs during the emergency? Did they meet the operational needs? | Capacity to timely increase human, material and financial resources and to safely deploy HR, efficiency for scaling up national and/or international HR (admin)
| Was there collaboration with partners for accessing additional personnel, equipment or financial resources? | Efficiency of mechanisms for mobilization and coordination of partners
Improve | What actions taken enabled a rapid and effective scale up of resources ? | Best practise for scaling up operations
| What challenges were encountered with the scale up of resources ? | Weaknesses for scaling up operations
Relevant documents to review
National emergency preparedness and response plan
Indicators
Time to needed to identify surge capacity
Additional questions

## Risk communication
Risk communication and community mobilization
Description: To review the functioning of risk communciation and community engagement plans in terms of available resources, staff and coordination during the response.
Trigger questions
| Questions | Discussion points
Document | How should risk communication and community mobilization be conducted? | Adequacy of means for risk communication and social mobilization, Existance of risk communication and social mobilization strategy/plan .
| How should messages be developed, cleared and communicated? | Existence of procedures for messages development, clearance and diffusion
Identify and analyse | How was risk communication implemented at community level and how were communities mobilized ? | Effectiveness of communication plans and strategy, availability of resources and trained staff
| How were risk communication activities and messages coordinated between levels of the health system (local, regional and national)? | internal coordination and communication, coordination of messages, dissemination of guidance,etc
| Who was communicated to, with what messages and how was communication enabled? | efficiency of mechanisms to define/clear messages and positionings, process for messages development, clearance and communication, complementarity and coordination with partners
| were sufficient resources available to conduct risk communication community mobilization? | trained human resource capacity, material and financial resources
| How were risk communication activities and messages coordinated with other sectors and partners? | coordination between sectors and partners on communication, management of any inconsistent messaging
| How was risk communication adapted and monitored for effectiveness throughout the emergency? Did this allow a timely and effective management of rumours and misinformation? | Mechanisms for activities monitoring and corrective measures, information sharing with partners, mobilization and involvement of partners, complementarity and coordination with partners
Improve | What actions taken improved the ability to communicate risks at community level, or the perceived mobilization of the community? | Best practise in risk communication and community mobilization
| What actions taken improved or limited the ability to detect and address rumors and misinformation? | Best practise and weaknesses in rumours/misinformation management
| What challenges were encountered in risk communication and community mobilization? | Weaknesses in risk communication and community mobilization
Relevant documents to review
National emergency preparedness and response plan
Communication strategy
Rumor management strategy and log
Indicators
Additional questions
Use of social media

## Public communication
Public Communication
Description: To review the effectiveness of existing plans for public communication in term of definition of public statements, designation of spoke person and use of media/language and to assess their effectiveness in building transparency and trust and in managing public concerns.
Trigger questions
| Questions | Discussion points
Document | How should public communication be conducted? By who? What is the process for developing and clearing positionning and public messages? | Describe public communication plans, strategy and procedures existing
Identify and analyse | How was public communication conducted during the emergency? Was a specific communication plan developed? | Efficiency of mechanisms to define and clear public messages and positionings, existence and use of designated spokespersons, interoperationality between communication plan and response,
| Was public communication sufficiently resourced during the emergency? | sufficient trained human resources for public communciation, sufficient funds and dedicated budget lines
| What was the process for clearing, coordinating and delivering communication products and messages? | Functioning of coordination structures for public communication, decision making messages, communciation in relevant languages, clearing of messages based on target audience and communication strategy.
| How was public communication coordinated with other sectors or partners? | coordination between sectors/partners on messaging, management of inconsistent messaging.
| How effective was public communication for building trust with public population and in managing emerging public concerns? | Efficient use of existing media platforms, efficient use of languages/messages, geographical coverage and use of social media for communication, impact studies on communication and revision of communciation plan, monitoring of rumors,etc
Improve | What actions enabled a timely and effective communication to the public or media? | best practises in public communication
| What challenges were encountered in communication to the media or public? | Challenges in public communication
Relevant documents to review
National emergency preparedness and response plan
Communication strategy
Press releases
Media reports
Press briefing transcripts
TV/radio
Indicators
Date of declaration of emergency
Date of declaration of end of emergency
Additional questions
How was social media used to communicate health messages?

## Information Management
Information Management
Description: To review action taken to manage and diseminate information in different forms and to diferent audience for the purpose of allowing decision making, raising awareness or mobilizing resources and support from national or international donors.
Trigger questions
| Questions | Discussion points
Document | What information products should normally be produced to keep partners and decision-makers informed? | Existence of strategy for collection, analysis and transmission of information
Identify and analyse | How was information managed during the emergency? What information products were developed ? Who and how were they distributed to? | Sitrep: Timeliness, quality/relevance Medical/epidemiological data: data collection, analysis and transmission
| Were sufficient tools and resources available for information management needs? | Human resources, tools and templates for information products,
| Did information products disseminated enable timely decision-making, fund-raising, etc? | Diffusion, relevance and usefulness of information produced
Improve | What actions taken enabled a timely and effective collection, analysis, compilation and distribution of information? | Best practise in information management
| What challenges were encountered to collect, analyse, compile and distribute information? | Weaknesses in information management
Relevant documents to review
National emergency preparedness and response plan
Sitreps
Other inforamation products
Indicators
Frequency of sitreps
Additional questions
Are there standard templates/form for funding proposal and financial reporting? Were they timely produced and did they meet donors expectations? |  | Funding proposal and reporting: timeliness, quality, acceptance by donors

## Finance Management
Finance Management
Description: To review actions taken to management funds during the response including the availability, accessing funds, timeliness and safety of payment and cash managmement and the maintenance of a financial overview and accountancy during the emergency.
Trigger questions
| Questions | Discussion points
Document | How should initial and emergency funds be made available during an emergency? | Existence of mechanism for accessing funds for emergency response start up
| What are the procedures for financial accounting during the response to an emergency? | Existence of tools, templates and accountability mechanism for finance management
Identify and analyse | How was finance management undertaken during the event | Systems and mechanisms for finance management: timely availability of funds, timeliness of payment/availability of cash, timely production of budgets, efficient mechanism for budget approval, efficient and transparent accountability systems
| How was coordination with donor managed during the event? | Relation and coordination with donors, tools and templates for fund-raising, donor reporting,
Improve | What actions taken enabled an effective access and accountability of funds? | Best practises in finance management
| What were the main challenges encountered in the financial managements in term of budget, cash-flow, payments, accountability and audit requirements? | Weaknesses in finance management
Relevant documents to review
National emergency preparedness and response plan
Response financial plan
Response funding proposals
Donor reports
Indicators
Initial funds made available
Additional funding received
Dates of external funds received
Additional questions

## Response phase-out and closing
Response phase-out and closing
Description: To review actions taken to declare the end of the emergency and to phase-out response activities in timely and effective manner.
Trigger questions
| Questions | Discussion points
Document | What process exists for managing the scaling down and phase out of the response? | Existance of SOPs for scaling down and closing an emergency response, existance of protocols for official declaration of end of emergency, existance of procedures for ressources reallocation
Identify and analyse | How was the scaling down and deactivation of the response managed? | Effectiveness of SOPs for scaling down and closure of a response
| What was the process accounting, reporting and reallocating human, financial and material resources remaining? | Transparent and effecient decision process for assets realocation
| How were final reports produced and reported to donors? | Existance of templates and tools, quality and timeliness of reporting
Improve | What actions taken allowed for a timely and efficient response deactivation and phase out? | Best practises in response phasing out and closing
| What challenges were encountered in the planning and managing the scaling down and the closure of the response phase? | Weaknesses in response phasing out and closing
Relevant documents to review
National emergency preparedness and response plan
Declaration of the end of the outbreak
Final emergency report
Indicators
Date of declaration of end of emergency
Additional questions

## Recovery
Recovery
Description: To review effectiveness in engaging in health sector recovery following the emergency, including coordination with other sectors in managing comprehensive recovery programme
Trigger questions
| Questions | Discussion points
Document | What plans exist for ensuring the recovery of a health system following an emergency? | Existence of health recovery plans, availability of resources, identification of responsabilities and key players within the MoH
| Do MoH plans integrate with multisectoral recovery plans and are the health sector role and responsabilities in recovery defined? | Existence of formal multisectoral coordination mechanism for recovery, representation of the health sector
Identify and analyse | What was the process for planning and implementing a recovery programme following the emergency? | Efficiency of existing health recovery plans, efficiency in transitioning from response to recovery structures, efficiency in accessing funds and in engaging in recovery activities, relevance of recovery activities
| Were sufficient resources available for engaging a comprehensive health sector recovery plan? | Trained staff to initiate and manage recovery transition, sufficient resources and funds to convene stakeholders and recovery planning and transition
| Did the recovery plan allow for effective and coordinated contribution of the health sector in recovery programs? | Efficiency of the health sector representation in recovery platforms, acceptance of health sector roles and responsabilitites, complementarity and coordination between health sector and others sectors
| If the recovery plan did not exist, how did the health sector engage in recovery processes and how efficient was it? | Process to produce a recovery strategy/plan, efficency in implementing this recovery plan
| How was the process of transition between response and recovery managed? | Efficiency of hand over between emergency response program and recovery program, efficiency in managing overlap between response and recovery programs
Improve | What actions taken during the event enabled the for grading, risk assessment or activation? | Best practise in grading and activation protocol
| What challenges were encountered during the grading, risk assessment or activation proccess? | Weaknesses in grading and activation protocol
Relevant documents to review
National emergency preparedness and response plan
Health sector recovery plan
Indicators
Additional questions

## Health system strengthening
Health system strengthening
Description: To review actions taken to or needed to Best practiseen and establish resilient health system in order to maintain routine health services during an emergency.
Trigger questions
| Questions | Discussion points
Document | How should the continuation of routine health services be ensured during an emergency? | Relevance of contingency plan for anticipation and mitigation of the impact of the event
| What existing plans inform the assessment of the impact of the event on the health system and how should corrective/reconstruction measures be implemented? | Existence of plans, SOPs for assessing the impact of the event on the health system, to identify key activities and to ensure availability of resources
Identify and analyse | During the emergency, what was the process for assessing the impact on health system and for maintaining health service delivery? | Efficient mechanisms and ressources for assessing impact of the event
| How was the maintenance of routine health services in the affected areas coordinated with health and non health partners? | coordination with stakeholders to maintain
| How was a plan for maintaining health services during and following this emergency developed and how efficient was its implementation? | Efficient mechanisms for producing action plans, timely availability of resources, timely and qualitative implementation of strengthening/reconstruction activities ?
Improve | What actions taken enabled resilience in providing routine health services during the emergency? | Best practises in health system strengthening ?
| What challenges were encountered being planning providing routine health services ? | Weaknesses in health system strengthening
Relevant documents to review
National emergency preparedness and response plan
Indicators
Additional questions