Tabletop Exercise (TTX) Project Checklist

Tabletop Exercise (TTX) Project Checklist

Conduct

Planning

☐ Scoping the TTX (i.e. Concept Note)

☐ Establish the Exercise Management Team

☐ Define the project management plan

☐ Identify the participants

☐ Define the evaluation strategy

☐ Manage admin tasks and logistics

☐ If required, media, PR and communications

☐ If required, safety and security

Material Development

☐ Review the Concept Note

☐ Context research & gather reference materials

☐ Develop the problem statements and scenario

☐ Write the injects

☐ Develop evaluation material

☐ Draft briefings

☐ Finalize the agenda and timing

☐ If required, draft opening or closing remarks

Set up

☐ Setup the exercise venue

☐ Brief the exercise management team

2-5 days

1 day

Exercise Conduct

Pre-Exercise

1 week

Results and Follow up

- ☐ Debrief the Exercise Management team

- ☐ Initial report to senior-level officials

- ☐ Develop the Exercise Report

- ☐ Close outstanding admin and logistics

- ☐ If required, Internal Mission Report

Post-Exercise

Conduct

- ☐ Welcome and opening

- ☐ Brief participants on the simulation exercise

- ☐ Start the exercise (i.e. present the narrative)

- ☐ Facilitate the exercise

- ☐ Capture the discussions

- ☐ End the exercise

- ☐ Exercise debrief

- ☐ Close the exercise

1-2 months prior to TTX

1 day