Conduct

Planning

☐ Scoping the DR (i.e. Concept Note)

☐ Establish the Exercise Management Team

☐ Define the project management plan

☐ Identify the participants

☐ Define the evaluation strategy

☐ Manage admin tasks and logistics

☐ If required, media, PR and communications

☐ If required, safety and security

Material Development

☐ Review the Concept Note

☐ Context research & gather reference materials

☐ Write the master scenario

☐ Develop the injects and inject matrix

☐ Develop evaluation material

☐ Develop the exercise handbook and/or briefings

Set up

☐ Setup the exercise venue

☐ Setup the exercise control room

☐ Check all equipment

☐ Brief the exercise management team

Drill Exercise (DR) Project Checklist

Drill Exercise (DR) Project Checklist

1 or more days

1 week

1 day

2 weeks

Exercise Conduct

Pre-Exercise

Results and Follow up

- ☐ Debrief the Exercise Management team

- ☐ Initial report to senior-level officials

- ☐ Develop the Exercise Report

- ☐ Close project admin and logistics

- ☐ If required, Internal Mission Report

Post-Exercise

Conduct

- ☐ Brief participants on the simulation exercise

- ☐ Start the exercise

- ☐ Run/control the exercise

- ☐ Capture the outcomes

- ☐ End the exercise

- ☐ Exercise debrief

- ☐ Close the exercise

1-2 months prior to DR