Functional Exercise (FX) Project Checklist

Conduct

Planning

☐ Scoping the FX (i.e. Concept Note)

☐ Establish the Exercise Management Team

☐ Define the project management plan

☐ Identify the participants

☐ Define the evaluation strategy

☐ Manage admin tasks and logistics

☐ If required, media, PR and communications

☐ If required, safety and security

Material Development

☐ Review the Concept Note

☐ Context research & gather reference materials

☐ Write the master scenario

☐ Develop the injects and inject matrix

☐ Fully develop and write out all planned injects

☐ Develop evaluation material

☐ Develop the exercise handbook and/or briefings

☐ If required, draft opening or closing remarks

Set up

☐ Setup the exercise venue(s)

☐ Setup the exercise control room

☐ Check all equipment

☐ Brief the exercise management team

Functional Exercise (FX) Project Checklist

1-3 days

1-5 days

4-6 weeks

1 week

Post-Exercise

Results and Follow up

- ☐ Debrief the Exercise Management team

- ☐ Initial report to senior-level officials

- ☐ Develop the Exercise Report

- ☐ Close project admin and logistics

- ☐ If required, Internal Mission Report

Conduct

- ☐ Welcome and opening

- ☐ Brief participants on the simulation exercise

- ☐ Start the exercise

- ☐ Run/control the exercise

- ☐ Capture the outcomes

- ☐ End the exercise

- ☐ Initial exercise debrief (Hot Wash)

- ☐ Main exercise debrief workshop

- ☐ Close the exercise

1-2 months prior to FX

Exercise Conduct

Pre-Exercise