Full-scale/Field Exercise (FSX) Project Checklist

*Field-exercises are usually shorter, Planning can begin 8 weeks prior to the exercise, Material Development is 8-10 weeks, Exercise Conduct is 1 week, and Post-exercise reporting is 2 weeks.

Conduct

Planning

☐ Scoping the FSX (i.e. Concept Note)

☐ Establish the Exercise Management Team

☐ Define the project management plan

☐ Identify the participants

☐ Define the evaluation strategy

☐ Manage admin tasks and logistics

☐ Media, PR and communications

☐ If required, safety and security

Material Development

☐ Review the Concept Note

☐ Context research & gather reference materials

☐ Write the master scenario

☐ Develop the injects and inject matrix

☐ Fully develop and write out all planned injects

☐ Develop evaluation material

☐ Develop the exercise handbook and/or briefings

☐ If required, opening or closing remarks

Set up

☐ Setup the exercise venue(s)

☐ Setup the exercise control room

☐ Check all equipment

☐ Brief the exercise management team

2-4 weeks*

6 months prior to FSX*

Exercise Conduct

Conduct

- ☐ Welcome and opening

- ☐ Brief participants on the simulation exercise

- ☐ Start the exercise

- ☐ Run/control the exercise

- ☐ Capture the outcomes

- ☐ End the exercise

- ☐ Initial exercise debrief (Hot Wash)

- ☐ Main exercise debrief workshop

- ☐ Close the exercise

Full-scale/Field Exercise (FSX) Project Checklist

Results and Follow up

- ☐ Debrief the Exercise Management team

- ☐ Initial report to senior-level officials

- ☐ Develop the Exercise Report

- ☐ Close project admin and logistics

- ☐ If required, Internal Mission Report

Post-Exercise

1-2 weeks*

1 week*

4-5 months*

Pre-Exercise