## Introduction
Introduction to the Exercise Planning Tool (EPT)
For exercises to be most effective, they should form part of a comprehensive programme made up of progressively complex exercises, each exercise building on the previous one until they are as close to reality as possible. This ‘building-block approach’ should start with basic exercises that test specific aspects of preparedness and response, followed by progressively complex exercises requiring additional preparation time and resources.
The main purpose of the WHO Exercise Planning Tool (EPT) is to support MoH partners in developing and setting-up a comprehensive exercise programme, especially in the worplan implementation and budgeting contexts.
The Tool is divided in 7 sections:
Exercise Overview Table This table is meant to be an overview on the various activities that compose an exercise programme. The table shows under which category the activities fall, a brief description of them, and the organizational details needed to implement the activities (Number of participants, duration, etc). This table should be used as a reference in the initial phases of the exercise programme planning.
Strategic Objective This sheet supports the user to articulate strategic objectives for the exercise programme. An exercise programme should be built around strategic objectives and each exercise planned within it, should contribute to achieving those strategic objective. Having clearly defined strategic objectives will ensure that the programme remains focussed and coherent, and that each exercise builds upon the other with increasing complexity over time.
Requirements Checklist This sheet is meant to be a overview of the requirements needed in order to organize an exercise programme. This sheet should be used as a reference during the initial phases of the exercise programme planning, in order to identify the requirements currently in place and the ones needed to be reached before moving to the following phases.
Exercise Selection In order to support the selection of the right type of exercise, WHO developed a decision tree including some key questions that can be considered in the selection process.
Exercise Calendar This sheet is the first part of the actual planning tool. With the knowledge from the first sections of the tool, and from the exercise planning session performed at country level, this table should be filled with the exercise programme for the country. The table is divided in 7 sections: Activity type: the type of activity planned. This column can be filled through the drop down menu of the single cell. In order to do so, single click on the selected cell and click the arrow that appears on the right side of it. Then, click on the type of activity wanted. Status: the status of implementation of the activity. This column can be filled through the drop down menu of the single cell. In order to do so, single click on the selected cell and click the arrow that appears on the right side of it. Then, click on the current status of implementation. Subject area: the area interested by the planned activity. Geographical location: the geographical location of the activity. Target audience: the audience meant to be reached by the activity Responsible planning: the organization/team/department responsible for the organization of the activity. Calendar: a calendar divided in weeks. It is suggest to report on it both the actual implementation dates of the activities and the planning time required to perform the activity. For example, if an activity requires 1 week to be implementated, but requires 4 weeks to be organized, the total of 5 weeks planning and implementation should be reported in the calendar.
Costing Tool The Costing tool helps to plan an estimate of the costs for each activity and the total for the exercise programme. This tool has automatic calculation of the total costs and of the partial breakdowns. The Checklist has 3 types of tables: The Fixed Costs: all the various activities shares types of expenditure that, on an estimate, stay fixed regardless of the the activity selected. This table should be used to list such costs . The excel file will automatically use the inputted values in the calculation of the costs. The activities tables: a table for each type of activity. Each table should be used to list the activity specific costs. The partial cost brreakdowns are calculated automatically, but for the total activity cost the number of activities planned must be inputted in the table in order to produce the total cost. Total Costs: A table that automatically lists the costs for activity and the total cost estimate of the exercise programme.
Other Possible Costs A table for keeping track on secondary expenditures linked to the exercise programme.

## Exercise Overview Table
Time and resources required to conduct an exercise will vary widely depending on the type of exercise, the scope and scale. The following table provides an indication for each of the exercise types.
Category | Exercise Type | Description | Organizational Exercise Experience | Scoping/planning missions 4-6 weeks before | Planning Resources | Planning Cost | Time for Preparation and Planning | Duration
Discussion Based Exercise | Table top exercise TTX | A Table-top exercise is a facilitated discussion of an emergency situation, in an informal, low-stress environment. It is designed to elicit constructive participant discussion, to identify and resolve problems and refine existing operational plans. | Low to medium | optional | Low to medium | Low to medium cost | Low to medium (a few days/weeks) | 0.5-1 day
Operational Based Exercises | Dril DR | A drill is a coordinated, supervised exercise activity, normally used to test a single specific operation or function. The drill aims to practice and perfect one small part of the response plan and should be as realistic as possible, employing any equipment or apparatus for the function being drilled. | Low to medium | optional | Medium | Low to medium cost | Low to medium (a few days/weeks) | 2-3 hours
| Functional Exercise FX | A functional exercise is a fully simulated interactive exercise that tests the capability of an organization to respond to a simulated event. The exercise tests multiple functions of the organization’s operational plan. It is a coordinated response to a situation in a time pressured, realistic simulation. A functional exercise focuses on the coordination, integration, and interaction of an organization’s policies, procedures, roles and responsibilities before, during, or after the simulated event | High | yes | Large amount of resources | Medium to High cost | Extensive planning and preparation (a few weeks) | 1-2 days
| Field/Full Scale Exercise FSX | A field or full-scale exercise simulates a real event as closely as possible and is designed to evaluate the operational capability of emergency management systems in a highly stressful environment, simulating actual response conditions. This includes the mobilization and movement of emergency personnel, equipment and resources. Ideally, the field/full-scale exercise should test and evaluate most functions of the emergency management plan or operational plan. | High | yes | Large amount of resources | High cost | Extensive planning and preparation (a few months) | 1-5 days

## Strategic objectives
Strategic Priorities & Exercise Programme Objectives
Exercises are not one-off events, but should be undertaken as part of a carefully designed exercise programme, that ensures a common strategic objective is addressed. The exercise programme forms a vital component of the emergency preparedness cycle. The components of the preparedness cycle are: planning; organizing; training; equipping; exercising; evaluating; and taking corrective action. After action reviews/lessons learned activities from real events also feed into the cycle, as illustrated below:
An exercise programme should be developed in accordance with the organizations` strategic priorities, by identifying the key capabilities most critical to their achievement and form an important part of emergency risk management. Each exercise planned , should contribute to achieving the strategic priorities and thus it is important that the overall strategic objectives of the organization are known.
Having clearly defined the organization`s strategic priority will better ensure you to define the objectives of your exercise programme that contributes to the organizations` mission. The objectives of the exercise programme will ensure that the programme remains focussed and coherent, and that each exercise builds upon the other with increasing complexity over time.
Below provides an example of an organizations` strategic priority and the objectives of an exercise programme:
Organizations` Strategic Priority:
Establish a programme of long-term development activities whose goals are to strengthen the overall capacity and capability of a country to manage efficiently all types of emergency and to bring about an orderly transition from relief through recovery and back to sustainable development.
Exercise programme objectives:
1) Develop and maintain simulation exercise tools
2) Implement all types of simulation exercises at all levels
3) Foster a network of simulation experts (facilitatrs)
Below provides the space to define the strategic priority of your organization, followed by the identification the objectives for the exercise programme
Organizations` Strategic Priority:
Exercise Programme Objectives:
1.
2.
3.
4.
5.

## Requirements checklist
The following is an rough overview of the key requirements to manage and implement an effective exercise programme:
Requirement | Description | Checkbox
Training and Risk Assessments | An exercise programme should be designed according to the results of risk assessments (planning) and training needs. A well-planned and well-implemented exercise programme helps ensure that risk assessments, training programmes and exercise events are consistent, progressive and focused on common goals that complement and build on one another. The programme should blend planning, organizing, training, equipping and exercise events to ensure that participants’ interest levels are maintained, and to reflect lessons from previous exercises, as well as actual emergencies.
Senior Management Commitment | This support is essential to argue for the utility and added benefit of the exercise and will provide the mandate to conduct the exercise. Senior management commitment will also help to allocate the necessary resources and will ensure that the purpose and objectives are in line with the overarching ERM programme. Furthermore, management backing can help to ensure that exercise outcomes/recommendations are used and followed up
Purpose & Objectives | The exercise purpose and objectives should be develeop as early as possible and should be based on an assessment of the needs which will help define the reasons to conduct the exercise and identify the functions to be tested. A well planned exercise is based on the definition of its aims and objectives which leads to relevant results and an efficient allocation of time and resources. A needs or risk assessment could entail, for example, the desk review of existing response plans.
Exercise Capacity | The capacity to support the development and the facilitation of the exercise is a fundamental element in any exercise. The exercise management will be responsible to plan, develop, implement and follow up on the exercise and its outcomes. The composition of an exercise management team varies per exercise, but generally speaking will consist of an exercise director and the exercise planning team. The exercise director is responsible for the planning and conduct of the exercise, whereas the exercise planning team supports the director with the preparations and the design of the simulation. The exercise management team might include members from outside the organization
Time | The planning of a simulation exercise depends on the complexity of the simulation (including the purpose, scope & objectives), the facilitation’s team simulation experience, and their other workload. Inexperienced facilitators or those with additional heavy workloads may require a longer lead time. In general less complex exercise require less planning time, while more complex exercise require longer planning (see exercise table in tab 1).
Budget | Direct costs of organizing a simulation vary depending on the type of exercise. In general they include travel and accommodation expenses for facilitators traveling from abroad, renting a venue, basic stationery and printing. For more info see `costing tool`sheet.
Resources | Admin & logs support, local context input and background documentation. The design and planning often requires a lot of local input to ensure realism, appropriateness and also advocacy to encourage participation from the target audience.

## Exercise Selection
In order to support the selection of the right type of exercise, WHO developed a decision tree including some key questions that can be considered in the selection process. Nevertheless, WHO places emphasis on a comprehensive exercise programme, made up of progressively complex exercises. Therefore it is recommended that organizations start with basic exercises first, before moving to more complex exercises.

## Exercise Calendar
| Exercises' Calendar | [6 empty] | LEGEND
[8 empty] | Training |  |  | Scoping/Planning Mission |  |  | Planning Preparation |  |  | Actual Event |  |  | Post exercise
WHO emphasis on adopting a comprehensive exercise programme, made up of progressively complex exercises, each one building on the previous one, until exercises are as close to reality as possible[1]. This ‘building-block approach’ is recommended for the exercise programme and should start with basic exercises that test specific aspects of preparedness and response. Following are more progressively complex exercises, requiring more preparation time and resources. Each exercise within the progressive series is linked to a set of common programme priorities and designed to test associated capabilities.
# | Activity type | Status | Subject area |  | Geographical Location | Target audience | Responsible planning | Mar-16 |  |  |  | Apr-16 |  |  |  | May-16 |  |  |  | Jun-16 |  |  |  | Jul-16 |  |  |  | 2016-08-01 |  |  |  | Sep-16 |  |  |  | Oct-16 |  |  |  | Nov-16 |  |  |  | Dec-16
|  |  |  | Location type |  |  |  | Wk1 | Wk2 | wk3 | Wk4 | Wk1 | Wk2 | wk3 | Wk4 | Wk1 | Wk2 | wk3 | Wk4 | Wk1 | Wk2 | wk3 | Wk4 | Wk1 | Wk2 | wk3 | Wk4 | Wk1 | Wk2 | wk3 | Wk4 | Wk1 | Wk2 | wk3 | Wk4 | Wk1 | Wk2 | wk3 | Wk4 | Wk1 | Wk2 | wk3 | Wk4 | Wk1 | Wk2 | wk3 | Wk4
1 | Tabletop Exercise | In progress | Emergency response plan | capital | Monrovia | EOC members | EOC and WHO | bar: Mar-16 Wk2; Apr-16 Wk2 to May-16 wk3
2 | Drill | Planned | RRT Mobilization | capital | Monrovia | RRT | WHO | bar: Apr-16 Wk1 to Apr-16 Wk2; May-16 Wk2 to Jun-16 Wk2
3 | Functional Exercise | Not started | EOC activation | outside capital | Border town of YYYY | EOC and stakeholders | EOC, MoH and WHO | bar: Apr-16 Wk4 to May-16 Wk2; Jun-16 Wk2 to Jul-16 Wk4
4 | Field/Full scale Exercise | Planned |  | outside capital | multiple |  | EOC, MoH, NGO, WHO, WFP, UNICEF | bar: Apr-16 Wk4 to May-16 wk3; Jun-16 wk3 to Jul-16 Wk1; Jul-16 Wk4; Sep-16 Wk1 to Nov-16 Wk2; Nov-16 Wk4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Costing tool
COSTING TOOL
| Currency used for this estimation |  | USD | <- enter USD or code of local curency
- Fill the table below with the estimated amount to budget for the following expenses. If some of your exercises will take place outside the capital city, please differentiate the costs accordingly
- Please refer to the Exercise budget template of the manual for a detailled breakdown of cost if necessary
- At this stage, use estimates for planning purpose. Detailled budget for each similation will have to be developped during the implementation of the exercises' programme.
| Estimated fixed costs for all exercises |  | Exercises in capital city | Exercises outside the capital city
| Average cost of flight per international expert |  | 1500 | 1500
| Daily Per diem per external expert |  | 250 | 250
| Average travel cost per national participant |  | 0 | 40
| Daily per diem per national participant |  | 12 | 40
| Conference room costs per day |  | 350 | 23
| Average costs of refreshment (2 coffee + lunch) per person & per day |  | 25 | 12
| Stationery (per event) |  | 340 | 99
| ICT equipment rental per day (projectors, printers, sound-system) |  |  | 66
| Medical consumables (for drills and full/field exercises) per event |  | 23 | 650
| Additional services (translation, security, actors,…) per event |  | 150 | 122
please fill all estimated fixed costs in the table above before proceeding to the next table
The table below is linked with the Exercise Calendar. Don't add or change the exercise description here. Please adjust or add directly in the calendar
| # | Exercise description |  |  | Number of international facilitators | Days of per diem for international facilitators | Number national participants, incl national facilitators, requiring travel | Number of Per Diem days for national participants and facilitators | Number of days of venue | Number of days of catering | Need for Stationery | Need for ICT equipment rental | Need for medical consumables | Need for additional services | type | international facil | national participant | conference room | catering | other costs | Estimate cost | Funds available | Funding source | Funding gap | Potential donor
| 1 | Drill - Emergency response plan (Monrovia) |  |  | 2 | 6 | 33 | 5 | 3 | 3 | yes | no | Yes | yes | 1 | 6000 | 1980 | 1050 | 2625 | 513 | 12168 | 3000 | MoH and WHO | 9168 | CDC, Japanese Embassy
| 2 | TTX - RRT Mobilization (Monrovia) |  |  | 1 | 6 | 12 | 5 | 3 | 3 | no | no |  |  | 1 | 3000 | 720 | 1050 | 975 | 0 | 5745 | 5745 | WHO | 0 | -
| 3 | FX - EOC activation (Border town of YYYY) |  |  | 3 | 6 | 10 | 5 | 7 | 7 |  | yes |  | yes | 2 | 9000 | 2400 | 161 | 1092 | 584 | 13237 | 7000 | MoH and CDC | 6237 | WHO (DFID project)
| 4 | FSX - No subject area specified (multiple) |  |  | 0 | 6 | 15 | 5 | 5 | 5 |  |  | yes | yes | 2 | 0 | 3600 | 115 | 900 | 772 | 5387 |  |  | 5387 | -
| 5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 6 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 7 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 9 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 10 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 11 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 12 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 13 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 14 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 15 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 16 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 17 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 18 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 19 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 20 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 21 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 22 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 23 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 24 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
| 25 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | -
[21 empty] | 36537 | 15745 |  | 20792

## Lists (hidden)
Activity type | Status | Cost type | location | Y/N
Tabletop Exercise | In progress | Procurement | capital | Yes
Drill | Not started | Training | outside capital | No
Functional Exercise |  | Running cost
Field/Full scale Exercise |  | Personnel