## Verification Gantt
Verification study Gantt chart
|  |  | MONTH 1 |  |  |  | MONTH 2 |  |  |  | MONTH 3 |  |  |  | MONTH 4 |  |  |  | MONTH 5 |  |  |  | MONTH 6 |  |  |  | MONTH 7 |  |  |  | MONTH 8 |  |  |  | MONTH 9
STAGE | ACTIVITIES | RESPONSIBLE | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1: PREPARATION | Define HIV testing strategies to be updated e.g. 3-test and ANC algorithms | MOH | bar: MONTH 1 W1
| Identify assays to be verified icluding back-up assays for A1, A2, A3 | MOH | bar: MONTH 1 W1
| Determine which new HIV assays are registered in-country or regionally | MOH | bar: MONTH 1 W1
| Determine the reference standard assays to be used in the study: RDT, EIA | MOH | bar: MONTH 1 W1
| Review and adapt scoring of the test selection tool according to the context | MOH | bar: MONTH 1 W1 to MONTH 1 W2
| Shortlist candidate assays using the test selection tool | MOH | bar: MONTH 1 W2
| Do quantification of test kits/materials needed according to study methodology | MOH | bar: MONTH 1 W3
| Develop budget of the study | MOH | bar: MONTH 1 W3
| Place order of test kits, materials and consumables | MOH | bar: MONTH 1 W4
Waiting time while supplies arrive in the country | bar: MONTH 1 W4 to MONTH 4 W4
| Select study site and staff and develop activities and responsabilities matrix | MOH | bar: MONTH 1 W2
| Determine verification specimen panel size and plan to collect specimens once study is ERB approved | MOH | bar: MONTH 1 W2
| Adapt study protocol along with data collection tools | MOH | bar: MONTH 1 W2
| Develop study database | MOH | bar: MONTH 1 W3 to MONTH 1 W4
2: EXECUTION | Start patient recruitment in selected clinics for specimen collection | MOH | bar: MONTH 4 W3 to MONTH 5 W1
| Establish verification specimen panel based on reference testing (true negative samples) | MOH | bar: MONTH 5 W1
| Conduct training of staff on each new HIV assay and data collection | MOH | bar: MONTH 5 W1
| Run verification panel with all candidate products including QC | MOH | bar: MONTH 5 W2 to MONTH 6 W2
| Conduct data analysis and selection of HIV testing algorithms | MOH | bar: MONTH 6 W3 to MONTH 6 W4
3: PILOT | Develop SOPs and job aids for the new HIV products | MOH | bar: MONTH 7 W1 to MONTH 7 W2
| Train clinic staff on the new HIV testing algorithm and data collection | MOH | bar: MONTH 7 W2 to MONTH 7 W3
| Run new HIV testing algorithms in selected clinics | MOH | bar: MONTH 7 W4 to MONTH 8 W4
| Collect data to assess feasibility and acceptability | MOH | bar: MONTH 9 W1
| Conduct data analysis | MOH | bar: MONTH 9 W2
| Write study report with findings and recommendations for scale-up | MOH | bar: MONTH 9 W3 to MONTH 9 W4
WHO/UCN/HHS/21.08
© World Health Organization 2021. Some rights reserved.
This work is available under the
CC BY-NC-SA 3.0 IGO licence