## Instructions
APPENDIX I-2: Sample Budget Calculator and Gantt Chart (Survey Timeline)
This Excel file includes a budget calculator template along with a sample budget for RDS and a sample Gantt Chart (depicting the survey timeline). This file is a reference as you prepare a budget and project timeline for a BBS. Please note that this calculator is for preliminary budgeting purposes; the line items should be adjusted accordingly for the specific budgetary needs of the survey and implementing institution. The categories covered are core components of a budget and are not exhaustive. For example, the budget includes some point of care (POC) tests and some laboratory tests -- all of these will not necessarily be used in every survey. This template should guide planning for surveys that may be completely POC. This calculator was not designed to be used as a bookkeeping tool or to track expenses; it is a tool for estimating costs in the budgeting process. Discuss with your agency how to track the exact costs. For actual pricing, contact each manufacturer for a specific quote. It is important to review the RDS and TLS sections of the Guidelines to determine the kind and the number of staff needed and related costs. When resources are limited or a survey is on a small scale, one person may perform multiple tasks.
Although not included in the Budget Calculator, the following two categories may need to be considered when preparing a budget:
Consultant costs | This category is appropriate when hiring an individual to give advice or services (e.g. training, expert consultant, etc.) for a fee but not as an employee of the organization.
Cost sharing | A subcontract may be required if a part of the survey effort will be performed by one or more other organizations.
Description of the Budget Calculator
| Color scheme | Description
Items that may be needed depending on survey type, such as RDS or TLS
Major budget categories
Inputs
Output
Subtotal of each category
Grand total of budget
Cell number | Title | Notes and Instructions
A5 | A. Personnel salaries/fringe benefits | Category A combines personnel salaries and fringe benefits. When needed, they can be separated into two entries. Fringe benefits are any nonwage payment or benefit granted to employees by employers. Examples include pension plans, profit-sharing programs, vacation pay, and company-paid life, health, and unemployment insurance.
B5 | Number needed | Enter the number of staff needed.
C5 | Annual salary | Enter annual salary.
D5 | No. of months | Enter the length of the survey in months. Different staff may work for different lengths. For example, a PI works the entire survey, but field staff work only while the survey is conducted in the field.
E5 | Time (%) | Enter percentage of time to show the effort contributed during the survey period. For example, a PI may have several projects and other responsibilities (such as teaching as a professor) at the same time. If the PI will contribute part of her/his time to the current survey, say 4 hours a week (40 hours), her/his percentage of time effort is 4/40=10%.
F5 | Salary total | Salary = annual salary*No. of Month/12*Time (%). It will be auto-filled.
G5 | Fringe rate | A fringe benefit rate is the cost of an employee's benefits divided by the wages paid for the hours working on the job. Some employees may not receive such benefit from their employer. Enter fringe rate for eligible staff. This can be 0 for non-eligible staff.
H5 | Total salary and fringe benefits | This is the total of salary+fringe rate*salary. This will be auto-filled.
A8 | Field staff | The staff listed here are some essential personnel. Staff may vary depending on the type and scale of the survey. The list can be expanded to add a staff for one specific function, or reduced if one staff can perform multiple duties in a smaller scaled survey setting.
A16 | Additional field staff for RDS | For RDS, there are additional needs, such as testing counselors, quantitative interviewers, qualitative interviewers, transcribers and translators in qualitative interview. The list can be expanded based on survey need, such as the object distributor during size estimation, cleaner, and security staff.
A17 | Data management/analysis staff | List staff for data management and data analysis. Some staff, such as a GIS developer, can be added depending on survey need. Or, in a small budgeted survey, data management and data analysis can be performed by one person.
A20 | Laboratory staff | For a survey that involves biomarker testing only. The list can be expanded based on survey need.
A28-C28 | B. Trainings and meetings | Training expenses, including the cost of the conference room, handouts, and other expenses, apply to any type of training or meeting. Enter number of participants for handout cost. Enter number days of training for conference room. For simplicity, the calculator lists only one training example for fieldwork preparation/size estimation. Other trainings/meetings that may need to be included in the calculator: Formative assessment training Survey implementation training Data analysis, interpretation, and writing workshop Community forum Local/national dissemination meeting
D28 | Number of participants | Enter the number of participants.
E28 | No. of units needed | Enter the quantity of handouts needed, including extra copies (e.g. 5 extra for a group of 20 participants).
F28 | Number of days | Enter number of days for conference room rental.
G28 | Cost per unit | Enter unit price for handouts, or rent per day.
A36-C36 | C. Fieldwork preparation, formative assessment, and size estimation implementation | Use this section to budget expenses for field preparation, formative assessment, and size estimation implementation.
A42 | Formative assessment preparation
A43 | Transportation for key informants and focus group participants | Enter number of participants and key informants, and unit price (cost per person).
A45 | Formative assessment supplies | Enter costs for maps, coupons, camera, audio recordings, batteries, etc.
A46 | Phone vouchers for formative assessment staff | Enter number of assessment staff and unit price.
A47 | Field work size estimation implementation | See above for Formative Assessment. Additional staff for distributing objects may be budgeted here also if they are not included in Section A (Personnel).
A44 | Unique objects for size estimation | Enter unit price for objects and number of participants.
A48 | Unique event | Enter number of days, and unit cost.
D53 | D. Survey implementation | Items listed in section D are items regularly used for survey implementation. This list may not include everything. Keep a detailed checklist for all supplies needed. Subcategories may be added for separate costs for RDS or TLS.
A74-H74 | E. Laboratory expenses | Complete this section if any biomarkers are used. The estimation of laboratory expenses is very complicated. Working with a laboratory professional to develop the budget is strongly recommended.
A76-B76 | INPUT box | The value for assumed prevalence in this block will help to generate numbers in the "OUTPUT" block (number of specimens) to calculate cost of consumables.
A77 | Number of participants | Enter number of participants.
A78 | Assumed HIV prevalence | Enter assumed HIV prevalence based on survey population. This is used for budgeting HIV biomarker consumables used to test blood samples from HIV-positive participants, such as for CD4 and VL.
A79 | Assumed syphilis prevalence | Enter assumed prevalence for syphilis among survey population to budget for syphilis biomarker consumables.
A80 | Assumed STI prevalence | Enter assumed prevalence for other STI to be surveyed, such as HCV, to budget for other STI biomarker consumables.
A81 | Number of trainees | Enter number of trainees in lab training, which may determine certain equipment needed, such as a timer.
A82 | Number of labs performing testing | The number of labs determines the number of certain equipment needed.
D76-G76 | OUTPUT (Number of specimens)
D77-F77 | Expected number of HIV positive | Calculated as: Assumed HIV prevalence*Number of participants
D78-F78 | Expected number of syphilis positive | Calculated as: Assumed syphilis prevalence*Number of participants
D79-F79 | Expected number of other STI positive | Calculated as: Assumed STI prevalence*Number of participants
A84 | Equipment | Equipment estimate assumes all required equipment needs to be purchased and therefore reflects a maximum cost. This calculator does not take into account equipment that may already be in place in individual laboratories. The equipment items may be expanded depending on the survey need, such as common equipment of plate washer, reagent reservoirs, etc. This section may be expanded according to survey needs. For example, for on-site testing and handling, mobile phones, tables, and chairs may be included.
A93 | Consumables for biomarkers testing | The consumables for laboratory assays listed can be revised according to survey need, such as HIV genotyping, HIV DR, TB, chlamydia, HSV, HBV, etc.
A103 | Consumables for blood collection | The list includes common items, It should be adjusted according to the survey.
A111 | Consumables for other specimen collection | See above.
A117 | Other consumables | Other items that may be considered here are: distilled or de-ionized water, Band-Aids, cotton balls, latex-free gloves, latex gloves (powdered and powder free), paper towels and absorbent covers for lab benches, marking pens, pads for lab table, hand soap, facemasks, zip lock bags, protective eyewear, bins and liners, paper towels, spray bottles, etc.
D84 | Manufacture & unit description | Enter brand/name of manufacture, catalog number, and description such as "10/pk, size large" for lab coat.
E84 | Unit dimension | Enter number of 1 unit here, such as "10" for 10-piece pack.
F84 | No. of units needed | Enter the number of units needed. The number of units for biomarkers are determined by estimated positive participants in the OUTPUT box, and Unit dimension, then multiplying by 110% for final units neede to account for 10% buffer.
G84 | Cost per unit | Enter price of unit.
A128 | For TLS | Please refer to TLS chapter for other costs/items, although only mobile van is listed here.
A129 | Mobile van and clinic rentals for HIV testing | If survey type is TLS, mobile van and clinc rentals for HIV testing may be needed. Please add any additional costs, such as gasoline and parking, if they are needed.
| Additional notes for point of care | The listed items in this section is not a comprehensive list of health services/care/treatment. Modify the budget as needed to account for specific point of care acitvities including STI treatment.
A132 | F. Travel | Cost for travel may be budgeted on an anticipated actual cost basis. The cost for consultant should be included in Consultant cost only.
A137 | G. Other expenses | Enter other expenses in this category. Revise accordingly to include items such as software, toner, postage, delivery fees, etc.
A161 | RDS survey sites | Refer to the RDS implementation chapter to add items.
A164 | Site maintenance | Including cleaning and bathroom: toilet cleaning, toilet paper, toilet brush, floor cleaner, mop, bucket, absorbent pad, washing liquid, dish drainer, sponge, and hand soap.
Description of the Gantt Chart of the Survey Timeline
Gantt charts are used for project management. They are helpful for defining and scheduling tasks and deadlines as well as tracking progress.

## Budget Calculator Template
BUDGET CALCULATOR TEMPLATE
NOTE: Please refer to Instructions (first tab) for use of this calculator
A. Personnel salaries/fringe benefits | Number needed | Annual salary | Number of months | Time (%) | Salary total | Fringe rate (% of salary total) | Total salary and fringe benefits
Principal investigator |  |  |  |  | 0 |  | 0
Project coordinator |  |  |  |  | 0 |  | 0
Field staff
Site supervisor |  |  |  |  | 0 |  | 0
Enumerator |  |  |  |  | 0 |  | 0
Coupon manager |  |  |  |  | 0 |  | 0
Interviewer |  |  |  |  | 0 |  | 0
Counselor |  |  |  |  | 0 |  | 0
Community outreach worker |  |  |  |  | 0 |  | 0
Driver |  |  |  |  | 0 |  | 0
Additional field staff |  |  |  |  | 0 |  | 0
Data management/analysis staff |  |  |  |  | 0
Data manager |  |  |  |  | 0 |  | 0
Data analyst |  |  |  |  | 0 |  | 0
Laboratory staff
Laboratory supervisor/coordinator |  |  |  |  | 0 |  | 0
Laboratory technician |  |  |  |  | 0 |  | 0
Phlebotomist |  |  |  |  | 0 |  | 0
Laboratory assistant |  |  |  |  | 0 |  | 0
Driver |  |  |  |  | 0 |  | 0
Subtotal: Personnel salaries and fringe benefits | [6 empty] | 0
B. Trainings and meetings |  |  | Number of participants | Number of units needed | Number of days | Cost per unit | Total
Fieldwork preparation/size estimation training
Conference room | [6 empty] | 0
Handouts | [6 empty] | 0
Refreshments
Transportation for meeting attendees
Subtotal: Trainings and meetings | [6 empty] | 0
C. Fieldwork preparation, formative assessment, and size estimation implementation |  |  | Number of participants | Units needed | Number of days | Cost per unit | Total
Site selection visits (RDS)
Car Hire + driver | [6 empty] | 0
Fuel | [6 empty] | 0
Compensation | [6 empty] | 0
Communication (Internet/phone calls, Mobile phones, Smart phones, External hard drive, USB 8 GB, internet hub) | [6 empty] | 0
Formative assessment
Transportation for key informants and focus group participants, and site selection visits | [6 empty] | 0
Formative assessment supplies | [6 empty] | 0
Phone vouchers for formative assessment staff | [6 empty] | 0
Field work size estimation implementation
Unique event | [6 empty] | 0
Unique objects for size estimation | [6 empty] | 0
Phone vouchers for size setimation staff | [6 empty] | 0
Subtotal: Fieldwork preparation | [6 empty] | 0
D. Survey implementation |  |  | Number of participants | Units needed | Number of days | Cost per unit | Total
General supplies and miscellaneous | [6 empty] | 0
Tablets | [6 empty] | 0
Fingerprint scanner | [6 empty] | 0
Software, incl. antivirus | [6 empty] | 0
Laptops | [6 empty] | 0
Scanner, printer and toner | [6 empty] | 0
Participants compensation (incentive) | [6 empty] | 0
Transport reimbursements for participants | [6 empty] | 0
Health referral brochure | [6 empty] | 0
Field team supplies (backpacks, clipboards, etc.) | [6 empty] | 0
Transportation of DBS cards to central office | [6 empty] | 0
Shipping and freight cost for lab equipment and consumables | [6 empty] | 0
Other operational expenses (e.g. utilities, equipment based on security) | [6 empty] | 0
For RDS
Printing of survey coupons | [6 empty] | 0
Secondary incentive RDS | [6 empty] | 0
For TLS
Clicker for enumerator | [6 empty] | 0
Subtotal: Survey implementation | [6 empty] | 0
E. Lab expenses
INPUT |  |  | OUTPUT (Number of specimens)
Number of participants |  |  | Expected number HIV positive |  |  | 0
Assumed HIV prevalence |  |  | Expected number syphilis positive |  |  | 0
Assumed syphilis prevalence |  |  | Expected number other STI positive |  |  | 0
Assumed STI prevalence
Number of trainees
Number of labs performing testing
Equipment |  |  | Manufacturer & unit description | Unit dimension | Number of units needed | Cost per unit | Total
Incubators | [6 empty] | 0
Standard mini-centrifuge | [6 empty] | 0
Countdown timers | [6 empty] | 0
Pipettes (disposable transfer pipettes, precision pipettes, etc.) | [6 empty] | 0
UPS Units | [6 empty] | 0
Power cord extension leads | [6 empty] | 0
Portable generator | [6 empty] | 0
Cooler boxes | [6 empty] | 0
Consumables for biomarker testing
DBS cards |  |  |  |  | #DIV/0! |  | #DIV/0!
Humidity monitoring cards |  |  |  |  | #DIV/0! |  | #DIV/0!
Desiccants |  |  |  |  | #DIV/0! |  | #DIV/0!
Consumables for CD4 testing |  |  |  |  | #DIV/0! |  | #DIV/0!
Consumables for VL testing |  |  |  |  | #DIV/0! |  | #DIV/0!
Consumables for syphilis testing |  |  |  |  | #DIV/0! |  | #DIV/0!
Consumable for HBsAg testing |  |  |  |  | #DIV/0! |  | #DIV/0!
Consumable for MTB testing |  |  |  |  | #DIV/0! |  | #DIV/0!
Other consumables for other STI testing |  |  |  |  | #DIV/0! |  | #DIV/0!
Consumables for blood collection
Needles | [6 empty] | 0
Tourniquets | [6 empty] | 0
Alcohol | [6 empty] | 0
Vacutainer tubes | [6 empty] | 0
Vacutainer sleeves | [6 empty] | 0
Vacutainer holder rack | [6 empty] | 0
Centrifuge tube | [6 empty] | 0
Consumables for other specimen collection
Vaginal swabs | [6 empty] | 0
Rectal swabs | [6 empty] | 0
Oral fluid | [6 empty] | 0
Sputum cup | [6 empty] | 0
Urine collection jars | [6 empty] | 0
Other consumables
Biohazard bags | [6 empty] | 0
Biohazard bag holder | [6 empty] | 0
Disinfectant/bleach | [6 empty] | 0
Sharps containers | [6 empty] | 0
Lab coats | [6 empty] | 0
Labels (water- and freeze-proof labels) | [6 empty] | 0
Gloves | [6 empty] | 0
Cotton balls | [6 empty] | 0
Bandages or adhesive tapes | [6 empty] | 0
Other | [6 empty] | 0
For TLS |  |  |  |  | Days needed | Cost per unit
Mobile van rental for HIV testing | [6 empty] | #REF!
Subtotal: Lab | [6 empty] | #DIV/0!
F. Travel |  |  | Number of trips | Per diem & lodging | Mileage | Rate per mile | Total
Local transportation (site visit)
Staff travel
Subtotal: Travel | [6 empty] | 0
G. Other expenses |  |  |  |  | Units needed | Cost per unit | Total
IRB fees | [6 empty] | 0
Cell phones | [6 empty] | 0
Air time | [6 empty] | 0
Internet | [6 empty] | 0
Report printing and dissemination | [6 empty] | 0
Other communication expenses (external hard drive, USB & internet hub)
Stationery | [6 empty] | 0
Paper per box (white and colored) | [6 empty] | 0
Pens | [6 empty] | 0
Highlighters | [6 empty] | 0
Sticky notes | [6 empty] | 0
White board | [6 empty] | 0
White board markers and permanent markers | [6 empty] | 0
Notebooks | [6 empty] | 0
Files and tabs for cabinet | [6 empty] | 0
Filing cabinet (4-drawer) | [6 empty] | 0
Folders | [6 empty] | 0
Stapler | [6 empty] | 0
Staples | [6 empty] | 0
Tape | [6 empty] | 0
Staple remover | [6 empty] | 0
Paper clips | [6 empty] | 0
Equipment (TV, video players) | [6 empty] | 0
RDS survey sites
Site facility rental | [6 empty] | 0
Utilities | [6 empty] | 0
Site maintenance | [6 empty] | 0
Furniture | [6 empty] | 0
Filing cabinet locking | [6 empty] | 0
Book shelf | [6 empty] | 0
Refrigerator | [6 empty] | 0
Subtotal: Other expenses | [6 empty] | 0
TOTAL BUDGET | [6 empty] | #DIV/0!

## Sample Budget for RDS
SAMPLE BUDGET FOR RDS*
NOTE: Amounts are in US$ based on conservative cost estimates in a moderately expensive city. RDS at one site, sample size=400
A. Personnel salaries/fringe benefits | Number needed | Annual salary | Number of months | Time (%) | Salary total | Fringe rate (% of salary total) | Total salary and fringe benefits
Principal investigator | 1 | 75000 | 12 | 10% | 7500 | 20% | 9000
Project coordinator | 1 | 50000 | 12 | 100% | 50000 | 15% | 57500
Field staff
Site supervisor | 1 | 15000 | 3 | 100% | 3750 | 0% | 3750
Interviewer | 2 | 8000 | 3 | 100% | 4000 | 0% | 4000
Counselor | 3 | 8000 | 6 | 100% | 12000 | 0% | 12000
Community outreach worker | 1 | 6000 | 3 | 100% | 1500 | 0% | 1500
Coupon manager | 1 | 6000 | 6 | 100% | 3000 | 0% | 3000
Security | 1 | 6000 | 3 | 100% | 1500 | 0% | 1500
Additional field staff (cleaner, receptionist) | 2 | 6000 | 6 | 100% | 6000 | 0% | 6000
Data management/analysis staff
Data manager/data analyst | 1 | 12000 | 12 | 100% | 12000 | 15% | 13800
Laboratory staff
Laboratory coordinator | 1 | 20000 | 12 | 10% | 2000 | 15% | 2300
Laboratory technician | 1 | 8000 | 3 | 100% | 2000 | 0% | 2000
Phlebotomist | 1 | 10000 | 3 | 100% | 2500 | 10% | 2750
Driver | 1 | 7000 | 3 | 100% | 1750 | 0% | 1750
Subtotal of Personnel Salaries and fringe benefits | [6 empty] | 120850
B. Trainings and meetings |  |  | Number of participants | Number of units needed | Number of days | Cost per unit | Total
Fieldwork preparation/size estimation training (6 participants)
Conference room |  |  |  | 1 | 2 | 100 | 200
Handouts |  |  |  | 10 |  | 5 | 50
Training expenses |  |  |  | 10 |  | 25 | 250
Formative assessment training (8 participants, 5 days)
Conference room |  |  |  | 1 | 5 | 100 | 500
Handouts |  |  |  | 12 |  | 10 | 120
Training expenses |  |  |  | 60 |  | 25 | 1500
RDS implementation training (10 participants, 10 days)
Conference room |  |  |  |  | 10 | 100 | 1000
Handouts |  |  |  | 14 |  | 10 | 140
Training expenses |  |  |  | 140 |  | 25 | 3500
Subtotal: Trainings and meetings | [6 empty] | 7260
C. Fieldwork preparation, formative assessment, and size estimation implementation |  |  |  | Number of participants | Units needed | Cost per unit | Total
Formative assessment
Unique event |  |  |  |  | 1 | 2000 | 2000
Unique objects for size estimation |  |  |  |  | 500 | 2 | 1000
Formative assessment supplies |  |  |  |  | 1 | 200 | 200
Transportation for key informants and focus group participants |  |  |  |  | 60 | 4 | 240
Phone vouchers for formative assessment staff |  |  |  |  | 18 | 20 | 360
Field work size estimation implementation
Unique event |  |  |  |  | 1 | 2000 | 2000
Unique objects for size estimation |  |  |  |  | 500 | 2 | 1000
Phone vouchers for size estimation staff |  |  |  |  | 18 | 20 | 360
Subtotal: Fieldwork preparation | [6 empty] | 7160
D. Survey implementation |  |  |  | Number of participants | Units needed | Cost per unit | Total
General supplies and miscellaneous
Notebook |  |  |  |  | 6 | 500 | 3000
Laptops |  |  |  |  | 1 | 1200 | 1200
Printing of survey coupons |  |  |  | 400 | 1200 | 2 | 2400
Printer and toner |  |  |  |  | 1 | 1000 | 1000
Reproduction/copies (6 months) |  |  |  |  | 6 | 100 | 600
Participant reimbursements |  |  |  | 400 | 440 | 10 | 4400
Participant secondary compensation x 3 |  |  |  | 400 | 1320 | 4 | 5280
Transport reimbursements for participants |  |  |  | 400 | 440 | 4 | 1760
Health referral brochures |  |  |  | 400 | 440 | 1 | 440
Field team supplies (backpacks, clipboards, etc.) |  |  |  |  | 10 | 40 | 400
Transport of DBS cards to central office |  |  |  |  | 12 | 50 | 600
Other operational expenses (e.g. utilities, equipment based on security) |  |  |  |  | 1 | 1000 | 1000
Subtotal: Survey implementation | [6 empty] | 22080
E. Lab expenses
INPUT |  |  | OUTPUT (Number of specimens)
Number of participants | 400 |  | Expected number of HIV positive |  |  | 100
Assumed HIV prevalence | 25%
Number of trainees | 4
Number of labs performing testing | 1
Equipment |  |  | Manufacture & unit description | Unit dimension | Number of units needed | Cost per unit | Total
Incubators |  |  | Fisher Scientific | 1 | 1 | 4800 | 4800
Standard mini-centrifuge |  |  | Fisher | 1 | 1 | 425 | 425
Countdown timers |  |  | Fisher Scientific | 1 | 4 | 50 | 200
Cooler box |  |  |  |  | 2 | 50 | 100
Consumables for biomarkers
DBS cards |  |  | Whatman, Pack of 100 | 100 | 5 | 800 | 4000
Other consumables
All other lab supplies |  |  |  |  | 1 | 5000 | 5000
Subtotal: Lab | [6 empty] | 14525
`
F. Travel |  |  | Number of trips | Per diem & lodging | Mileage | Rate per mile | Total
Local transportation (site visit) |  |  | 1 |  |  |  | 2000
Subtotal: Travel | [6 empty] | 2000
G. Other expenses |  |  |  |  | Unit needed | Cost per unit | Total
IRB fees |  |  |  |  | 1 | 200 | 200
Cell phones |  |  |  |  | 2 | 100 | 200
Air time (10 staff, 6 months) |  |  |  |  | 10 | 120 | 1200
Internet |  |  |  |  | 12 | 300 | 3600
RDS survey sites
Site facility rental |  |  |  |  | 6 | 1500 | 9000
Utilities |  |  |  |  | 6 | 100 | 600
Site maintenance |  |  |  |  | 6 | 50 | 300
Filing cabinet |  |  |  |  | 2 | 100 | 200
Bookshelf |  |  |  |  | 1 | 100 | 100
Refrigerator |  |  |  |  | 1 | 600 | 600
Subtotal: Other expenses | [6 empty] | 16000
TOTAL BUDGET | [6 empty] | 189875
*Global Strategic Information. Toolbox for conducting integrated HIV bio-behavioral surveillance (IBBS) in key populations. University of California, San Francisco. 2014. pp. 131–133.

## Gantt Chart Survey Timeline
SAMPLE GANTT CHART - SURVEY TIMELINE
Proposed Activity | Month
| 2017 | [8 empty] | 2018
| Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Formative Protocol Development | bar: 2017 Mar
Formative Protocol Approval | bar: 2017 Apr
Formative Training | bar: 2017 Apr
Formative Implementation | bar: 2017 Apr to 2017 May
Formative Assessment analysis | bar: 2017 May to 2017 Jun
Pre-test tools | bar: 2017 Jun
Protocol Development | bar: 2017 Mar to 2017 Jun
SOPs adapted | bar: 2017 Apr to 2017 Jun
Submit protocols and receive approval from all IRBs, <Country> Ethics Committee | bar: 2017 Jun to 2017 Aug
Recruit study team | bar: 2017 Jul
Development of data collection systems | bar: 2017 Apr to 2017 Aug
Study Implementation Training | bar: 2017 Aug
Study Implementation | [9 empty] | X | X | bar: 2017 Sep to 2017 Nov
Data cleaning/lab QA/data merging | [9 empty] | X | X | X | bar: 2017 Sep to 2017 Nov
Data analysis and preliminary report | [11 empty] | X | X
Present preliminary findings to stakeholders | [12 empty] | X
Final Report | [13 empty] | X
National Dissemination Workshop | [13 empty] | X