## General Instructions
Rabies Vaccine Introduction Situation Analysis Checklist
Given the many unique aspects of Rabies vaccination, a situation analysis is essential for developing strategies and planning.
This is adapted from the Guide to introducing human rabies vaccine into national immunization programmes (link on the document cover), available at: https://www.who.int/publications/i/item/9789240052499.
The situation analysis checklist should be used during the Planning stage vaccine introduction, to identify key information and data needed to plan effective strategies for rabies PEP vaccine delivery, including: - strengthening collaboration and coordination between primary health care, EPI and rabies programmes to leverage existing efforts - opportunities for comprehensive rabies control through linking human rabies PEP vaccine with animal health activities - where applicable, training and supervision of community health workers who are able to administer vaccines
Rabies Vaccine Introduction Readiness Assessment Tool
1 | The assessment tool consists of a national and a subnational-level. Suggestions for optimal timing and intervals are shaded in yellow for both levels.
2 | Update completion status of activities by choosing Complete, In progress, or Not Started from the dropdown menu in the timeline boxes.
3 | At the bottom of both the national and subnational levels, summary results of the activities and activity components completed at each monitoring/ supervisory visit are calculated in a number and percentage of the total number of critical preparation activities. Activities completed and in progress will contribute to score up until 2 weeks before launch of vaccine introduction rollout. At 1 week, only activites marked 'complete' should be counted to confirm readiness.

## SITUATION ANALYSIS
SITUATION ANALYSIS - Key questions to inform plan and strategy development
STAKEHOLDERS
Who are the key focal point(s) to work with in rabies within the health system ? (for example within the Ministry of Health covering rabies and EPI*). *EPI = Expanded Programme on Immunization
Which other partners can assist with rabies vaccination? (for example Gavi, WHO and UNICEF).
Which civil society/professional organizations should be engaged? (for example NGOs, medical and nursing associations, veterinary organisations, animal welfare organisations).
DATA TO INFORM VACCINATION STRATEGY
Burden of rabies e.g. number of human rabies cases disaggregated by gender and age.
Information on current PEP delivery - number of people receiving PEP, accessibility of PEP, route of administration for vaccine, RIG availability.
Animal bite burden - disaggregated by biting animal.
Rabies in dogs - number of animals tested, number of positives
Mass dog vaccination campaigns - location, frequency, number of vaccines administered, implementing agency, dog populaiton estimates if available etc.
Are facilities selected for rollout already providing immunisation services with adequate staffing?
Do facilities selected for rollout have sufficient cold chain capacity* and clean water with wound washing facilities ? *Cold chain specification for Rabies vaccines is provided in the Guide to introducing human rabies vaccine into national immunization programmes page 17.
Who has the clinical authority to administer vaccines (doctors, nurses)?
How will data be collected and reported? Which indicators will be used? How will PEP completion be ensured?
COORDINATION WITH OTHER SECTORS AND ACTIVITIES
How will access to human rabies vaccines be integrated with delivery of immunisation and other primary health care services.
Is healthcare worker training planned where rabies vaccine can be integrated?
Are animal health professionals trained to conduct a health assessment on offending animal? Can they access the animal in a timely manner? Have they received rabies PrEP?
Is there capability to notify human public health and animal health authorities of suspected rabies exposures?
Is there integration of human and animal data and surveillance such as data sharing mechanisms e.g. the ability to receive animal rabies diagnostic results?
Is there community-based activities (including educational activities, dog bite prevention, responsible ownership, dog population control measures) that may provide an opportunity for integration?
SUPPLY AND COLD CHAIN
How will rabies vaccine be provided to health facilities being considered for rollout?
What percentage of health facilities being considered for rollout that have a functioning cold chain? Are the facilities being considered currently providing immunisaiton services or will cold chain capacity need to be established in the proposed centres?
What vaccine, route of administration and schedule is currently in use? Is there going to be a change to intradermal administration ?
Can existing cold chain accommodate rabies vaccine? Is freeze monitoring in place?
CAPACITY BUILDING, SUPERVISION, UPDATING
Who will train healthcare staff on rabies PEP vaccine implementation/how will they be trained?
How will monitoring/supervision of vaccine rollout in health facilities be conducted?
How will EPI protocols and forms be updated?

## NATIONAL READINESS MACROPLAN
Rabies Vaccine Introduction Readiness Assessment Tool | [5 empty] | Planned rabies vaccine introduction start date:
Completed? Enter "Y" or "N" each time reviewed
Yellow indicates Ideal time prior to vaccine introduction to complete the activity
|  | Critical activities desired timeframe for completion shaded light yellow - green items also appear in subnational checklist | 12-10m | 9-7m | 6-4m | 3-2m | 1m | 2wk | 1wk | If not completed, indicate reason and status | Action required | Deadline | Person responsible MOH & TA partners
Date of review
1. PLANNING AND COORDINATION | 1.1 | Political commitment at all levels
| 1.2 | NITAG recommendation available - endorsing ID use where applicable
| 1.3 | Operational plan developed for rabies vaccine introduction, including target introduction date, vaccine delivery strategies and schedule, consideration of integration opportunities with EPI
| 1.4 | Rabies vaccine delivery strategy/schedule confirmed and SOPs updated including exposure assessment- to reflect WHO decision tree
| 1.5 | National Technical Working Group (TWG) or Coordination team established with appropriate participation, including by the national rabies control programme, EPI and animal health partners, and meeting regularly
| 1.6 | TWG subcommittees established or engagement of existing groups (which may be in place for other vaccine programmes), with TORs for: 1) technical/service delivery 2) cold chain & logistics 3) advocacy, communication and social mobilization (ACSM), 4) monitoring and evaluation, and 5) Safety/AEFI surveillance 6) One Health
| 1.7 | Briefings with TWG, MOH and other sub-national stakeholders on geographical areas for roll-out held
| 1.8 | Special strategies planned for geographically hard-to-reach and underserved populations, including specifically for rural populations and children
| 1.9 | Special strategies planned for opportunistic PrEP vaccination for those at occupational risk
| 1.1 | National Rabies vaccine introduction microplanning tools prepared
| 1.11 | National Rabies vaccine introduction microplanning tools distributed
2. FUNDING | 2.1 | Introduction budget and available funding sources (including VIG and potential additional GAVI funds) reviewed and potential gaps identified
| 2.2 | Vaccine Introduction Grant (VIG) funds received by MOH
| 2.3 | Additional funds mobilized to include RIG and animal health activites as part of comprehensive control plan
| 2.4 | Funds available to the district level for operational costs
3. TRAINING | 3.1 | Training plan developed
| 3.2 | Training materials developed and adapted to local contexts
| 3.3 | Training materials distributed to all districts
| 3.4 | Training of trainers carried out at national and sub-national level
| 3.5 | Training of health workers, community health volunteers and supervisors carried out
4. INTEGRATION | 4.1 | Identify potential rabies vaccine delivery strategies and service providers leveraging both existing vaccination platforms and non-vaccination delivery approaches to best reach identified target groups.
| 4.2 | Coordinate with national rabies disease surveillance group to ensure relevant epidemiological human and animal data will be collected to inform prioritisation planning, including outbreak responses.
5.MONITORING & SUPERVISION | 5.1 | A set of monitoring indicators for rabies developed and reviewed at national level *Annex D - WHO Guide to introducing human rabies vaccine
| 5.2 | Monitoring tools updated to include rabies (electronic data systems, vaccination card, monitoring charts, tally sheets, reporting forms, registers, supervisory checklists, AEFI reporting forms etc.)
AEFI monitoring system in place
| 5.3 | Monitoring tools printed and distributed to district level
| 5.4 | Training for use of monitoring tools and processes integrated within healthcare worker training
| 5.5 | Pre-introduction supervisory visits conducted to assess readiness for introduction
| 5.6 | Post-Introduction evaluation (PIE) planned and budgeted
6.VACCINE, COLD CHAIN & LOGISTICS | 6.1 | Vaccine licensure/registration granted by NRA
| 6.2 | Confirmation of vaccine delivery date received
| 6.3 | Rabies Immunoglobulin (RIG) procurement and logistics
| 6.4 | Additional commodities for wound care (e.g. wound dressings, antibiotics, tetanus vaccines etc) ordered to be available for introduction
| 6.5 | Cold-chain assessment completed at all levels and action taken for any gaps
| 6.6 | Waste management assessment completed and action taken for any gaps
| 6.7 | Tracking/monitoring system for vaccine supply management in place
| 6.8 | Vaccine and injection supplies received and distributed to regional and district level
7. ADVOCACY, COMMUNICATION & SOCIAL MOBILIZATION | 7.1 | A budgeted national plan for advocacy, communication, and social mobilization(ACSM) developed and finalized
| 7.2 | ACSM materials developed, validated and translated (print materials, radio/TV announcements, social media, etc.)
| 7.3 | Risk communication and management plan developed and key actors briefed and trained (spokesperson training)
| 7.4 | Key messages and FAQs developed
| 7.5 | Communication plan implemented and meetings held with partners and stakeholders (Ministries; NGOs, professional / scientific societies, media/journalists & civil society groups)
| 7.6 | ACSM materials distributed to health facilities, community leaders, communities and other key stakeholders
| 7.7 | Launch for rabies vaccine introduction planned (if applicable)
|  | Total Yes score on key items (in Yellow boxes): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *>2wk, 1 point is given for Complete and In Progress. By 1 wk, all must be Complete to get 1 point
|  | Target number of ongoing/completed activities (yellow) | 18 | 30 | 38 | 44 | 44 | 44 | 43
|  | Score % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Score: Fully (>95% score)
|  | Is the national level on track to introduce rabies vaccine as scheduled? | [7 empty] | Partially (95%< score < 80%)
Off track (< 80%)
Provide overall comment on progress/areas that need attention:
At6m
At3m
At2m
At1m
At2wk
At1wk

## SUBNATIONAL READINESS MICROPLAN
Rabies Vaccine Introduction Readiness Assessment - Subnational Tool
|  | Province: ____________ District:________________ | [5 empty] | Planned rabies vaccine introduction start date: _____/____/____
Name of supervisor/monitor: _______________________________
Completed? Write "Yes"or "No" each time reviewed
|  | Critical activities desired timeframe for completion shaded light yellow - green items also appear in subnational checklist | 3m | 2m | 1m | 2wk | 1wk | If not completed, indicate reason and status | Follow up action required | Deadline | Person responsible
Date of Review
1. PLANNING AND COORDINATION | 1.1 | Coordination team established (or engagement of existing group) at district level including participation from EPI and animal health
| 1.2 | District-level operational plans developed (including a list of focal points) developed for 1) vaccine supply and cold chain, 2) waste management, 3) safety monitoring, 4) training, 5) social mobilization and communication and 6) reporting and data analysis including human and animal rabies surveillance data
| 1.3 | Microplans finalized (including identification of at risk populations, health facilities, hard-to-reach populations, etc.)
| 1.4 | Special strategies planned for patients who present to health facilities which do not carry vaccine and private practicioners/pharmacies
2. FUNDING | 2.1 | Funds received for all planned activities
| 2.2 | Funds distributed for all planned activities appropriately
3. TRAINING | 3.1 | Health workers trained
| 3.2 | Community health volunteers trained
| 3.3 | Supervisors identified and trained
4. MONITORING & SUPERVISION | 4.1 | Supervision plan developed including visit dates, health facilities and names of supervisors for pre-launch readiness assessment and post-introduction visits
| 4.2 | Monitoring tools received at district level
| 4.3 | Monitoring tools delivered at health facilities
| 4.4 | Training for use of monitoring tools and processes conducted
5. VACCINES, COLD CHAIN & LOGISTICS | 5.1 | Sufficient cold-chain capacity confirmed at district level
- 5.1a refrigerators
- 5.1b cold boxes
- 5.1c vaccine carriers
| 5.2 | Sufficient cold-chain capacity (or contingency plans) confirmed at all facilities to deliver vaccine
| 5.3 | Waste management assessment completed and action taken for any gaps
| 5.4 | Tracking/monitoring system for vaccine supply management in place
Vaccines and supplied delivered in adequate quantitiy to health facilities (indicate completion status for each below);
| 5.5 | Vaccines | [5 empty] | Note # received
| 5.6 | AD syringes | [5 empty] | Note # received
| 5.7 | RUP reconstitution syringes | [5 empty] | Note # received
| 5.8 | Safety boxes
| 5.9 | Additional commodities (e.g. RIG, wound dressings, antibiotics, tetanus vaccines etc) | [5 empty] | Note # received
6. ADVOCACY, COMMUNICATION & SOCIAL MOBILIZATION | 6.1 | ACSM materials delivered to health facilities, community leaders, communities and other key stakeholders
| 6.2 | ACSM activities implemented according to the microplan
| 6.3 | Community awareness of launch
|  | Total Yes score on key items (Yellow): | 0 | 0 | 0 | 0 | 0 | *>2wk, 1 point is given for Complete and In Progress. By 1 wk, all must be Complete to get 1 point
|  |  | 19 | 22 | 28 | 28
|  | Score% | 0% | 0% | 0% | 0% | #DIV/0!
|  | Is the district on track to launch rabies vaccine introduction? (Y/N) | [5 empty] | Yes : Score ≥ 80%
No: Score < 80%

## Reference Page
Global guidance documents
Num | Category | Title | Date | Link | Type | Description | Issuing Dept
1 | 1. Planning and Coordination | Guide to introducing human rabies vaccine into national immunization programmes | 2020 | https://www.who.int/publications/i/item/9789240052499 | Technical Document | Provides step-by-step guidance for integrating human rabies vaccines into national immunization programmes, including planning, stakeholder engagement, and cold chain management. | WHO Global
2 | 1. Planning and Coordination | Zero by 30: The Global Strategic Plan to End Human Deaths from Dog-Mediated Rabies by 2030 | Ongoing | https://www.who.int/publications/i/item/9789241513838 | Technical Document | This document outlines the global strategy for eliminating dog-mediated rabies by 2030 through coordinated efforts across human and animal health sectors. | WHO Global
3 | 1. Planning and Coordination | Rabies vaccines: WHO position paper | 2018 | https://www.who.int/publications/i/item/who-wer9316 | Technical Document | This position paper provides updated recommendations on the use of rabies vaccines for post-exposure (PEP) and pre-exposure (PrEP) prophylaxis. It outlines the effectiveness, safety, and best practices for vaccine administration, including the use of intradermal injections for cost-effective rabies prevention in high-risk areas. | WHO Global
4 | 1. Planning and Coordination | Rabies Post-Exposure Prophylaxis Decision Tree: Decide with Confidence | Ongoing | https://cdn.who.int/media/docs/default-source/searo/ntd/who-searo_rabies-pep-decision-tree-poster.pdf?sfvrsn=f2249312_6 | Technical Document | Provides a visual guide for healthcare workers to assess and manage rabies post-exposure prophylaxis (PEP). | WHO SEARO
5 | 1. Planning and Coordination | Principles and considerations for adding a vaccine to a national immunization programme: from decision to implementation and monitoring | 2014 | https://iris.who.int/handle/10665/111548 | Technical Document | The document highlights the impact of vaccine introduction on immunization programs and health systems, offering strategies to minimize negative effects and maximize benefits. | WHO Global
6 | 1. Planning and Coordination | WHO-UNICEF guidelines for comprehensive multi-year planning for immunization: update September 2013 | 2014 | https://iris.who.int/handle/10665/100618 | Guidelines | This guide presents a series of steps to develop a comprehensive multi-year plan for immunization (cMYP), and includes both a planning tool and a costing tool. | WHO Global
7 | 1. Planning and Coordination | WHO Prequalified Vaccines | Ongoing | https://extranet.who.int/prequal/vaccines/prequalified-vaccines | Resource | A database listing vaccines prequalified by WHO for procurement and use in national immunization programmes, including rabies vaccines. | WHO Global
8 | 1, Planning and Coordination | Template for Landscaping of Resource Partners for Rabies | 2022 | https://www.unitedagainstrabies.org/uar-best-practice/landscaping-of-resource-partners-for-rabies-template/ | Template | assist stakeholders in landscaping resource partners within their country that could support rabies prevention and control. | United Against Rabies Forum
9 | 2. Funding | Gavi funding guidelines | 2024 | https://www.gavi.org/sites/default/files/support/guidelines-2024/GAVI-Vaccine-Funding-Guidelines-june2024.pdf | Guidelines | Details GAVI's funding mechanisms and eligibility criteria for rabies vaccine introduction. | GAVI
10 | 2. Funding | Gavi Vaccine Funding Guidelines (June 2024) | 2024 | https://www.gavi.org/sites/default/files/support/guidelines-2024/GAVI-Vaccine-Funding-Guidelines-june2024.pdf | Guidelines | GAVI funds and additional financial sources for VIG | GAVI
11 | 2. Funding | Rabies; rationale for investment in the global elimination of dog-mediated human rabies | 2015 | https://www.who.int/publications/i/item/9789241509558 | Technical Document | Provides key rationale for comprehensive investment in rabies control including summary of case examples. | WHO Global
12 | 2. Funding | Ending the neglect to attain the sustainable development goals: One health: approach for action against neglected tropical diseases 2021-2030 | 2022 | https://iris.who.int/handle/10665/351193 | Technical Document | Companion document to the WHO NTD Roadmap aims to support a range of stakeholders to achieve the road map targets through a transdisciplinary, cross-cutting One Health approach. | WHO Global
13 | 3. Training | WHO Academy Rabies & One Health | Ongoing | https://whoacademy.org/coursewares/course-v1:WHOAcademy-Hosted+H0051EN+H0051EN_Q4_2024?source=edX | Course | An online training course on rabies prevention and control, emphasizing a One Health approach and practical implementation strategies. | WHO Academy
14 | 3. Training | Training for mid-level managers (MLM): Module 4; supportive supervision | 2020 | https://iris.who.int/bitstream/handle/10665/337056/9789240015692-eng.pdf | Technical Document | Technichal document surrounding training for mid-level managers surrounding supportive supervision. | WHO Global
15 | 3. Training | EPI Mid-Level Management Online Training | Ongoing | https://app.who-afro-mlm.com/en-US | Course | Online course to provide MLM training to provide the essential technichal and managerial skills needed to run an immunization program at any level. | WHO AFRO
16 | 3. Training | Protocol for a well-performed rabies post-exposure prophylaxis delivery: to read along with the decision trees 1- Wound risk assessment and 2 - PEP risk assessment | 2024 | Protocol for a well-performed rabies post-exposure prophylaxis delivery: to read along with the decision trees 1- Wound risk assessment and 2 - PEP risk assessment | Technical Document | Protocol for a well-performed rabies post-exposure prophylaxis delivery: to read along with the decision trees 1- Wound risk assessment and 2 - PEP risk assessment. | WHO Global
17 | 4. Integration - data | Routine health information system and health facility data for neglected tropical diseases | Pending | Pending | Technical Document | This document mainly addresses the collection and analysis of individual data on the treatment of rabies exposures including PEP and rabies cases collected at rabies treatment centres/health facilities. | WHO Global
18 | 4. Integration - data | Minimum Data Elements for Monitoring and Evaluation of National and International Rabies Control Programs. | 2023 | https://www.unitedagainstrabies.org/wp-content/uploads/2023/09/2023_MinimumDataElements_V4_Sep2023_EN.pdf | Technical Document | This document provides a recommended structure for data collation as well suggested data collection templates, and suggestions for how these Minimum Data Elements (MDE) should be used to support evidence-based rabies policies. | United Against Rabies Forum
19 | 4. Integration - data | WHO Rabies Data Reporting Template | Ongoing | https://www.who.int/publications/m/item/who-rabies-data-reporting-template | Template | Template for reporting rabies data | WHO Global
20 | 4. Integration - data | Working together: An integration resource guide for planning and strengthening immunization services throughout the life course | 2018 | https://www.who.int/publications/i/item/9789241514736 | Technical Document | Overview of the global policies, potential interventions and strategies related to the integration of immunization services. provides guidance and country examples on the integration of immunization with additional health interventions | WHO Global
21 | 5. Monitoring and Supervision | WHO best practices for injections and related procedures toolkit | Ongoing | https://www.who.int/publications/i/item/9789240052499 | Toolkit | Provides guidelines for safe injection practices, including rabies vaccine administration and AEFI reporting | WHO Global
22 | 5. Monitoring and Supervision | Standard AEFI investigation form | 2021 | https://cdn.who.int/media/docs/default-source/pvg/new-standard-aefi-reporting-form-dec-2020-c.pdf?sfvrsn=978b9555_1&download=true | Template | Template AEFI investigation form | WHO Global
23 | 5. Monitoring and Supervision | ‘Zero by 30’ Monitoring and Evaluation Indicators | 2025 | https://www.unitedagainstrabies.org/wp-content/uploads/2025/02/2025_ZeroBy30_ME_Indicators_V1_EN.pdf | Technical Document | This document contains the Monitoring and Evaluation (M&E) indicators developed by the United Against Rabies Forum for ‘Zero by 30: the Global Strategic Plan to end human deaths from dog-mediated rabies by 2030’ | United Against Rabies Forum
24 | 6. Vaccines, Cold Chain and Logistics | How to monitor temperatures in the vaccine supply chain | 2015 | https://iris.who.int/bitstream/handle/10665/183583/WHO_IVB_15.04_eng.pdf?sequence=1&isAllowed=y | Technical Document | Correct use of available temperature monitoring devices for routine monitoring of cold chain equipment performance, temperature mapping of cold chain equipment and implementation of studies to assess supply chain temperatures. | WHO Global
25 | 6. Vaccines, Cold Chain and Logistics | WHO best practices for injections and related procedures toolkit | Ongoing | https://www.who.int/publications/i/item/9789240052499 | Toolkit | Provides guidelines for safe injection practices, including rabies vaccine administration and AEFI reporting | WHO Global
26 | 6. Vaccines, Cold Chain and Logistics | Cold Chain Equipment Inventory and Gap Analysis Tool | 2023 | https://www.who.int/publications/m/item/cold-chain-equipment-inventory-and-gap-analysis-tool | Tool | A planning tool for conducting and analysing a cold chain equipment inventory. | WHO Global
27 | 7. ACSM | Rabies Public Information Toolkit | 2023 | https://www.unitedagainstrabies.org/uar-best-practice/rabies-public-information-toolkit/ | Toolkit | This toolkit is designed for human and animal health authorities to inform the public about rabies and encourage responsible dog ownership, health-seeking behaviour, dog vaccination and reporting of suspected rabies cases. | United Against Rabies Forum
28 | 7. ACSM | WHO Strategic Communications Framework for Effective Communications | 2017 | https://www.who.int/docs/default-source/documents/communicating-for-health/communication-framework.pdf?sfvrsn=93aa6138_0 | Technical Document | The Framework is intended propose principles and tactics that be applied by communicators developing specific regional, disease-focused, or events-based strategies, so that their communications are actionable, accessible, relevant, timely, understandable, and credible. | WHO Global
29 | 7. ACSM | New vaccine introduction: checklist for planning communication and advocacy: World Health Organization vaccine safety supporting document | 2017 | https://www.who.int/europe/publications/i/item/WHO-EURO-2017-3375-43134-60388 | Technical Document | This document proposes a simple step-wise process for planning communication and advocacy for a new vaccine introduction. | WHO EURO
30 | 7. ACSM | Vaccine Messaging Guide | 2020 | https://www.unicef.org/documents/vaccine-messaging-guide | Technical Document | This guide can be used by all communications and advocacy colleagues to help develop messaging and content which can help build confidence and trust in vaccines. | UNICEF