## Sheet1
Section | Information needed | Means of obtanining information | Details | Notes | Progress
[5 empty] | Not started | In progress | Done
1. Purpose of framework | a. Purpose of the document b. Government expectations from all NTD and WASH partners | a and b. MoH focal point in consultation with core group (e.g. WASH ministry partner, technical working group) |  | Validate in workshop
2. Background | a. NTD statistics b. WASH statistics (access) c. Importance of WASH for NTDs d. Policy context: global and national e. Action taken so far on WASH-NTDs collaboration f. Link between this collaboration and the national health and development agenda | a-d, f. Document review (NTD master plan, national WASH reports, WASH-NTD toolkit, WHO NTD roadmap) e. MoH focal point |  | Include official data to ensure buy-in from stakeholders
3. Location and targeting of programme activities Basis for prioritizing implementation units (IUs) for increased WASH investment and collaboration | Assessment of disease distribution in the country and WASH conditions in the same areas (preferably district level). [If not possible in time for framework publication, the framework should include details of when/how this will be done] | Options (see STEP 3: Analysing the situation - Data for decision-making and supplementary tools): 1. Data merge: using an existing WASH or NTD platform or database to add additional information (for instance, adding WASH data to an NTD database, or vice versa), for use on an ongoing basis. 2. Decision matrix for one-off data collection and analysis, pulling together data from multiple sources onto an Excel-based tool. 3. Analysis using existing ESPEN NTD Portal WASH and NTD information.
4. Coordination Purpose of coordination/collaboration Structures for coordination | a. Key principles for collaboration b. Key actions by all stakeholders c. WASH sector decision-making and coordination structure d. NTD decision-making and coordination structure e. WASH-NTD coordination group and posts (e.g. TWG and coordinator/focal point) | a. MoH focal point with core group or TWG b. Workshop discussion c. Document review - including situation analysis, if this has been completed d. Document review - including situation analysis, if this has been completed e. Document review (e.g. ToR for TWG and for coordinator/focal point) | a. Can include aspects such as accountability, transparency, respect, inclusion etc. | In workshop, consider group work to discuss: i) actions to support coordination and joint planning; ii) timing of and process for annual planning in each sector, and for joint annual planning and budgeting; iii) data needed for joint planning and to ensure it is available in time; iv) barriers and opportunities for joint planning.
5. Joint planning | a. Planning schedule of each sector b. Joint planning schedule | a and b. Document review (e.g. national planning guidelines) and workshop discussion
6. Integration interventions designed to meet WASH and NTDs objectives and delivered through a single entry point | a. Existing programme guidelines (e.g. for health outreach, IMCI, school health) b. Remuneration guidelines (e.g. per diems/incentives for community health volunteers) c. Minimum aspects to be included in all programmes d. Structures to be involved (community health and school health clubs, any others) e. How equity and inclusion should be ensured f. List of integrated interventions and delivery mechanisms (in table format, provided separately) | a and b. Document review c. Workshop discussion d. Document review and workshop discussion e. Workshop discussion f. Workshop discussion | Workshop discussion using a pre-prepared intervention table for participants to populate is recommended. | Establish what is meant by "integrated interventions" before group work. Interventions such as routine provision of water supplies, for example, should not be included. But inclusion of hygiene promotion messages during social mobilization for MDA would be relevant.
7. Technical programme quality quality standards to be adhered to by all stakeholders when implementing WASH and NTDs interventions | a. WASH infrastructure: Reference or links to WASH infrastructure national standards or guidelines and national targets b. Behaviour change c. NTD programme standards | a-c. Document review | a. Can include provision standards (e.g. number of people served per borehole, pupil/toilet ratio in schools); water quality standards; construction standards for water supply and sanitation; disability-inclusive infrastructure requirements; user fee tariffs/regulations; service provider accreditation; operation and maintenance requirements. b. Existing behaviour change strategies; requirements for use of evidence in the design of behaviour change interventions/materials; consultation structures; links with other existing behaviour change campaigns/programmes. c. Can include any standards specified in the NTD Master Plan or guidance issued by WHO. | Workshop can be used to request relevant documents from participants. Not all types of documents listed here will be available in every country but where they exist, they shoud be referenced in the framework.
8. Monitoring, evaluation and reporting | a. Structure/process for including data on WASH access, use and functionality in NTD programme baseline, routine monitoring and evaluation surveys, including indicators b. Structure/process for routine data sharing at all levels to support planning and coordination including data sources and information systems to be used, and the level and frequency of data provided through these sources c. Routine programme monitoring and supervision process d. Mechanism for tracking and reporting financial investment on WASH and NTDs services to endemic populations e. Process for documenting and publishing programme lessons and outcomes | a. Workshop discussion unless already established b. Workshop discussion c. Workshop discussion unless already established d. Workshop discussion and discussion with finance officials to ascertain existing financial tracking system and agree relevant changes/additions e. Workshop discussion | This section may require further discussion and follow up after a workshop since: * Adoption of new indicators may require further discussions as well as modifications to monitoring systems and databases that require engagement of other institutions/departments. * Financial tracking requires discussion with ministerial finance departments and possibly ministry of finance to establish relevant codes and clarify financial tracking systems. * Existing field supervision protocols may need to be revised. * Programme reporting requirements (particularly by external support agencies or civil society organizations to government) may require further clarification. | Suggested group work questions: i) How can data on WASH and NTDs be collected for routine monitoring and evaluation? [core tool 11 can be used]; ii) How should joint monitoring and supervision be conducted [core tool 9]; iii) How can financial investment in WASH and NTDs be tracked through the existing financial system? iv) How can we best document and share lessons on WASH-NTDs collaboration to improve programme quality, enhance accountability, and mobilize resources?
9. Annexes | As relevant/available: a. Key policy documents b. Lists of key indicators (including any process indicators for WASH-NTDs coordination) c. Additional statistics d. Case studies/lessons from past/existing coordinated or integrated programmes e. Any key definitions needed to ensure that all stakeholders have a shared understanding (some suggested in template)